## Projects
| Projects KPI Dashboard | OPS Scanners Capacity | OSR | Rates Estimates | [5 empty] | Original Estimates | [5 empty] | Team Manager's end date estimates |  |  | Live Project Tracking
Project Code | Project Name | Production % Complete | Lead | Circuit Length (km) | ROW (km) | Area (km2) | SPU Factor | Total SPUs | Bid Total | RS Total | GIS Total | PLS Total | Production Total | Production Start date | Production Estimated Completion Date | RS (Luke) | GIS (Dom) | PLS (Carlos) | Staffology Time Entries | Remaining Hours | Variance | SPUs Delivered | PM end date | Archived
NMIP22035 | NYPA 2022 Group A | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 216 | 454 | 843 | 1513 | 2023-01-30 | 2023-05-22 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMAP23006 | Transgrid 2023 | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 2158 | 2574 | 2251 | 6983 | 2023-02-20 | 2023-07-17 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23026 | Xcel SPS TX HB | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 360 | 885 | 0 | 1245 | 2023-02-20 | 2023-05-22 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23005 | Ameren Spring 2023 | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 490 | 816 | 559 | 1865 | 2023-03-07 | 2023-07-10 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP22135 | NYSEG & RGE TLD 2022 | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 710 | 1336 | 0 | 2046 | 2023-05-01 | 2023-09-08 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23014 | Avangrid CMP & NY | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 60 | 75 | 36 | 171 | 2023-05-08 | 2023-06-19 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23028 | Xcel Colorado | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 160 | 245 | 0 | 405 | 2023-06-05 | 2023-07-17 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23016 | LS Power Tx | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 43 | 38 | 16 | 97 | 2023-06-12 | 2023-07-03 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23035 | NYPA 2023 Group B | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 131 | 315 | 431 | 877 | 2023-07-01 | 2023-10-27 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMAP26036 | Humelink Canopies | 30.7% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 182 | 28 | 60 | N/A | 88 | 2026-05-01 | 2026-06-19 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMCP22118 | Altalink Bull Trail Wind | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 18 | 34 | 3 | 55 | 2023-07-03 | 2023-07-24 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23029 | NGUS E5-F6 Mapping | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 4 | 16 | 4 | 24 | 2023-07-03 | 2023-07-17 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23019 | Southern Company GPC | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 899 | 1639 | 0 | 2538 | 2023-07-10 | 2023-10-31 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23042 | NGUS TLE 2023 | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 632 | 808 | 1774 | 3214 | 2023-07-10 | 2023-12-18 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23056 | Southern Company APC | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 427 | 637 | 0 | 1064 | 2023-07-10 | 2023-10-31 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMCP23017 | HONI | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 965 | 1846 | 1375 | 4186 | 2023-08-14 | 2024-02-16 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23065 | ComEd Will County | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 24 | 26 | 41 | 91 | 2023-08-21 | 2023-10-13 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23066 | ComEd Hodgkins Design | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 22 | 24 | 8 | 54 | 2023-08-21 | 2023-09-20 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23070 | Xcel Colorado Veg | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 614 | 911 | 0 | 1525 | 2023-09-01 | 2023-11-24 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23084 | Xcel NSP Summer | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 170 | 200 | 0 | 370 | 2023-09-11 | 2023-10-20 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMLP23024 | NIE 2023 | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 39 | 41 | 153 | 233 | 2023-09-11 | 2023-11-03 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMCP25092 | HONI Max Op | 100% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 872 | N/A | N/A | 2025 | 2025 | 2026-02-20 | 2026-06-05 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMCP25127 | HONI 500kV | 72% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 24 | 30 | 32 | 86 | 2026-05-08 | 2026-06-19 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMCP26023 | HONI 2026 | 2% |  | #NAME? | #NAME? |  | #NAME? | #NAME? | 8558 | 420 | 5000 | 878 | 6298 | 2026-05-22 | 2026-12-18 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP23068 | Santee Cooper Marion-Red Bluff | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 35 | 37 | 39 | 111 | 2023-09-18 | 2023-10-13 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23060 | Minnkota | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 92 | 194 | 116 | 402 | 2023-09-25 | 2024-01-12 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMLP23034 | NGUK | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 832 | 480 | 0 | 1312 | 2023-10-09 | 2024-02-29 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23080 | LS Power Manning | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 28 | 36 | 0 | 64 | 2023-10-16 | 2023-11-03 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23082 | NGUS T20 Mapping | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 4 | 14 | 0 | 18 | 2023-10-23 | 2023-10-31 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23045 | Eversource 2023 | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 946 | 1688 | 0 | 2634 | 2023-11-06 | 2024-01-29 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23102 | LGE Fall | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 354 | 68 | 72 | 494 | 2023-11-06 | 2024-01-22 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23094 | 3 Phase Line Construction V148S | 100% | PIT | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 8 | 16 | 8 | 32 | 2023-11-20 | 2023-11-27 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23077 | CMP Veg | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 90 | 210 | 0 | 300 | 2023-11-27 | 2024-02-09 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23087 | CMP Engineering | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 100 | 260 | 0 | 360 | 2023-11-27 | 2024-02-02 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23110 | NGUS Twin States Mapping | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 13 | 89 | 0 | 102 | 2023-11-27 | 2024-01-05 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23111 | NGUS B&M | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 50 | 34 | 10 | 94 | 2023-11-27 | 2024-02-28 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23115 | Xcel NSP | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 430 | 520 | 0 | 950 | 2023-12-04 | 2024-02-16 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23113 | ComEd Putnam | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 86 | 118 | 240 | 444 | 2023-12-18 | 2024-02-08 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMLP22148 | SSE T3 | 100% | PIT | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 40 | 40 | 16 | 96 | 2023-12-20 | 2024-01-31 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23104 | Ameren | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 600 | 1320 | 0 | 1920 | 2024-01-02 | 2024-04-18 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMLP23124 | SSE Braco West-Fasnakyle | 100% | PIT | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  |  | 40 | 2024-01-05 | 2024-02-01 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23101 | FPL 2024 | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 438 | 668 | 1957 | 3063 | 2024-01-08 | 2024-05-17 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23123 | LGE Paris | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 24 | 32 | 10 | 66 | 2024-01-08 | 2024-01-22 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMAP24001 | Transgrid 2024 | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 2878 | 3777 | 879 | 7534 | 2024-01-22 | 2024-05-31 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24010 | Xcel SBS House Bill | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 540 | 560 | 0 | 1100 | 2024-01-22 | 2024-04-12 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23117 | Santee Cooper | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 40 | 169 | 19 | 228 | 2024-02-12 | 2024-03-18 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMLP24027 | SSE Fort Augustus | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 40 | 50 | 0 | 90 | 2024-03-04 | 2024-03-21 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23126 | Ameren Winter 2024 | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 210 | 775 |  | 985 | 2024-03-11 | 2024-05-02 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMAP24028 | UGL CopperString | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 1102 | 1732 | 0 | 2834 | 2024-04-08 | 2024-07-04 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24034 | ComEd Rockford Freeport | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 28 | 58 | 15 | 101 | 2024-04-14 | 2024-05-20 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMLP24051 | SSE Arbroath | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 3 | 3 | 0 | 6 | 2024-04-15 | 2024-04-17 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24018 | NYPA Group C | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 148 | 487 | 462 | 1097 | 2024-05-06 | 2024-07-08 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24045 | Xcel LRTP | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 130 | 215 |  | 345 | 2024-05-06 | 2024-05-30 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23118 | LS Power CEEC | 100% | PIT | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 45 | 26 | 14 | 85 | 2024-05-20 | 2024-06-17 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24006 | Eversource Year 4 | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 380 | 2330 |  | 2710 | 2024-05-20 | 2024-08-07 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMLP24007 | NIE 2024 | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 85 | 90 | 247 | 422 | 2024-05-20 | 2024-07-01 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMLP24055 | SSE St Fillans | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | [5 empty] | 2024-05-28 | 2024-07-08 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24005 | LGE Spring 2024 | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 103 | 312 | 259 | 674 | 2024-06-05 | 2024-07-26 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24004 | NGUS 2024 | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 878 | 1988 | 3160 | 6026 | 2024-06-10 | 2024-12-13 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMAP24064 | Transgrid UAV | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 14 | 35 | 2 | 51 | 2024-06-11 | 2024-09-20 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24011 | NYSEG Montour Falls | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 14 | 55 |  | 69 | 2024-06-17 | 2024-06-28 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24065 | NYSEG L963-978 | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 14 | 40 |  | 54 | 2024-06-17 | 2024-06-28 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24060 | Avangrid RGE | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 14 | 25 |  | 39 | 2024-06-24 | 2024-07-12 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMLP24063 | SSE Tomatin | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 14 | 25 |  | 39 | 2024-06-24 | 2024-07-10 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMLP24049 | SSE Fansnakyle | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  |  | 0 | 2024-06-28 | 2024-07-12 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24014 | SoCo APC | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 500 | 1465 |  | 1965 | 2024-07-01 | 2024-10-31 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24015 | SoCo GPC | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 700 | 2100 |  | 2800 | 2024-07-01 | 2024-11-29 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMCP24052 | HONI Longwood | 100% | Team 3 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 91 | 148 | 24 | 263 | 2024-07-15 | 2024-08-12 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMCP24067 | HONI Durham | 100% | Team 3 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 25 | 24 | 6 | 55 | 2024-07-15 | 2024-08-12 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMCP24072 | HONI Darlington | 100% | Team 3 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  |  | 0 | 2024-07-15 | 2024-08-12 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24003 | FPL Summer 2024 | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 391 | 925.5 | 1801 | 3117.5 | 2024-07-29 | 2025-01-15 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24066 | NGUS 3D Mapping | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 13 | 17 |  | 30 | 2024-08-05 | 2024-09-16 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24081 | NGUS Mapping B154/C155 | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 4 | 9 |  | 13 | 2024-08-05 | 2024-09-16 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMLP24083 | Omexom Whistlefield | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  |  | 0 | 2024-08-09 | 2024-09-05 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMCP24017 | HONI 2024 | 100% | Luke | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 3232.5 | 4381.11 | 4547.9 | 12161.51 | 2024-08-10 | 2025-11-15 | -- | 2025-05-30 | 2025-05-30 | #REF! |  |  | #NAME? |  | TRUE
NMIP24075 | Xcel NSP | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 295 | 620 |  | 915 | 2024-09-05 | 2024-11-22 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24018-1 | NYPA group C VI | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 14 | 58 | 67 | 139 | 2024-10-04 | 2024-11-07 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMAP24087 | UGL Additional Processing | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 125 | 415 |  | 540 | 2024-10-21 | 2024-12-02 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24109 | Santee Cooper Fall 2024 | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 17 | 20 | 6 | 43 | 2024-10-21 | 2024-12-20 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24021 | LGE Fall 2024 | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 215 | 245 | 334 | 794 | 2024-10-24 | 2024-12-06 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23019-1 | SoCo GPC Reprocessing | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | 660 |  |  | 2024-11-04 | 2024-12-12 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24012 | CMP Veg 2024 | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 61 | 140 |  | 201 | 2024-11-04 | 2024-12-13 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24094 | CMP Engineering Fall 2024 | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 30 | 68 |  | 98 | 2024-11-04 | 2024-12-13 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMLP24016 | NGUK 2024 | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 840 | 560 |  | 1400 | 2024-11-04 | 2025-01-31 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMLP24102 | Skyports UAV | 100% | PIT | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 16 | 74 | 0 | 90 | 2024-11-15 | 2024-11-29 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24112 | ComEd Metro | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 10 | 90 | 59 | 159 | 2024-12-09 | 2024-12-27 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMLP24105 | SSE Tummel | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | [5 empty] | 2024-12-18 | 2024-12-20 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24117 | NYSEG | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 180 | 300 |  | 480 | 2024-12-23 | 2025-01-24 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP24019 | Ameren | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 310 | 490 |  | 800 | 2025-01-06 | 2025-02-07 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP25014 | Santee Cooper Lake Murray | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 41 | 48 | 8 | 97 | 2025-02-03 | 2025-02-21 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMAP25005 | Transgrid 2025 | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 1786 | 2580 | 316 | 4682 | 2025-02-10 | 2025-05-31 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP25009 | Ameren Winter 2025 | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 90 | 275 |  | 365 | 2025-02-24 | 2025-03-07 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP25018 | Xcel SPS HB Texas | 100% | Dom | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 330 | 883 |  | 1213 | 2025-02-26 |  |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMLP25023 | SSE XCW | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | [5 empty] | 2025-03-03 | 2025-03-07 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMLP24119 | NIE 2025 | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 28 | 30 | 2 | 60 | 2025-03-17 | 2025-04-04 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMLP24104 | SSE BDUP | 100% | Dom | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 105 | 45 | 150 | 300 | 2025-03-31 |  |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP25015 | OPPD Spring 2025 | 100% | Carlos | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 86 | 110 | 306 | 502 | 2025-04-03 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP25011 | Avangrid CMP Veg | 100% | Dom | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 135 | 310 |  | 445 | 2025-04-28 |  | -- |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP25016 | Power Engineers Rev Wind | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 23 | 48 |  | 71 | 2025-04-28 | 2025-05-16 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP25017 | Holyoke | 100% | Dom | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 23 | 35 | 80 | 138 | 2025-04-28 |  |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP25044 | Avangrid CMP Sub | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 23 | 29 |  | 52 | 2025-04-30 | 2025-05-16 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP25012 | NYPA Group D | 100% | Carlos | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 117 | 854 | 730 | 1701 | 2025-05-19 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP25010 | Eversource 2025 | 100% | Dom | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 950 | 2780 | 60 | 3790 | 2025-06-05 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP25054 | SoCo APC 2025 | 100% | Dom | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 2510 | 1430 | N/A | 3940 | 2025-06-24 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMCP25032 | HONI Patrol 2025 | 100% | Carlos | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 992 | 1152 | 347 | 2491 | 2025-06-26 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP25007 | NGUS TLE | 100% | Luke | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 422 | 808 | 1668 | 2898 | 2025-06-26 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP25066 | FPL 2025 | 100% | Carlos | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 805 | 170 | 217 | 562 | 949 | 2025-07-02 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP25057 | SoCo GPC 2025 | 100% | Dom | #NAME? | #NAME? |  | #NAME? | #NAME? |  | 1590 | 1000 | N/A | 2590 | 2025-07-18 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP25067 | Xcel 5301 | 100% | Dom | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 8 | 30 | N/A | 38 | 2025-07-21 |  | 2025-07-21 |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP25078 | ComEd L0709/L0710 | 100% | Sev | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | -- | 3 | -- | 3 | 2025-08-11 | 2025-08-11 | -- | -- | -- | #REF! |  |  | #NAME? |  | TRUE
NMLP25003 | NGUK 2025 | 100% | Luke | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1007 | 510 | 560 | N/A | 1070 | 2025-09-09 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMCP25083 | HONI 115 kV Reporting | 100% | Carlos | #NAME? | #NAME? |  | #NAME? | #NAME? |  | -- | 120 | 80 | 200 | 2025-09-11 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP25103 | Xcel MNEC | 100% | PIT | #NAME? | #NAME? |  | #NAME? | #NAME? |  | 8 | 16 | - |  | 2025-10-22 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMCP24067-4 | HONI DKPL | 100% | PIT | #NAME? | #NAME? |  | #NAME? | #NAME? |  | - | 8 | - | 8 | 2025-11-05 | 2025-11-05 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP25091 | Xcel PSCo Fall | 100% | Dom | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 95 | 200 | - | 295 | 2025-11-06 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP25093 | SoCo GPC Engr | 100% | PIT | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 25 | 35 | 49 | 109 | 2025-11-06 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP25104 | Xcel NSP Fall 2025 | 100% | Dom | #NAME? | #NAME? |  | #NAME? | #NAME? | 1694 | 370 | 580 | - | 950 | 2025-11-06 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP25049 | Minnkota PC 2025 | 100% | Carlos | #NAME? | #NAME? |  | #NAME? | #NAME? |  | 48 | 87 | 237 | 372 | 2025-11-07 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP25086 | NGUS ACR | 100% | Luke | #NAME? | #NAME? |  | #NAME? | #NAME? |  | 25 | 90 |  | 115 | 2025-11-11 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP25088 | NGUS Fall TLE | 100% | Luke | #NAME? | #NAME? |  | #NAME? | #NAME? |  | 55 | 80 | 146 | 281 | 2025-11-11 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP25052 | LGE Spring 2025 | 100% | Luke | #NAME? | #NAME? |  | #NAME? | #NAME? | 675 | 78 | 207 | 343 | 628 | 2025-11-14 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMCP26060 | HONI Darlington Nuclear | 0% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 30 | 8 | 8 | N/A | 16 |  |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP26003 | FPL Winter 2026 | 100% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1449 | 240 | 420 | 1029 | 1689 | 2026-01-23 | 2026-05-29 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP26002 | CHGE Spring 2026 | 88% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 239 | 90 | 50 | 193 | 333 | 2026-04-17 | 2026-06-19 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP25098 | LGE Fall (Eng) | 100% | Luke | #NAME? | #NAME? |  | #NAME? | #NAME? | 2516 | 155 | 130 | 167 | 452 | 2025-11-14 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP25109 | Ameren Drone | 100% | Dom | #NAME? | #NAME? |  | #NAME? | #NAME? |  | 8 | 20 |  | 28 | 2025-11-14 | 2025-11-25 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP25028 | Lansing BWL LiDAR | 100% | Carlos | #NAME? | #NAME? |  | #NAME? | #NAME? | 350 | 74 | 153 | 289 | 516 | 2025-11-20 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP25101 | HDR (NPPD) | 100% | Dom | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 80 |  | 32 |  | 32 | 2025-11-24 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP26008 | Avangrid CMP Veg 2026 | 73% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 788 | 195 | 400 | 89 | 684 | 2026-04-24 | 2026-06-26 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP26020 | FPL Summer 2026 | 0% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 145 |  | 975 |  | 2026-08-14 | 2026-12-04 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP26025 | Sunflower Electric | 70% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 529 | 270 | 900 | N/A | 1170 | 2026-05-15 | 2026-07-31 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP26027 | NYPA Group A 2026 | 27% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 2155 | 215 | 1000 | 1369 | 2584 | 2026-04-24 | 2026-08-14 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP26029 | NGUS 2026 | 0% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 2974 | 325 | 750 | 2123 | 3198 | 2026-07-24 | 2026-12-04 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP26032 | Westwood Minnesota | 100% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 62 | 24 |  |  | 24 | 2026-06-12 | 2026-06-19 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP26030 | OPPD 2026 | 88% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 784 | 105 | 100 | 367 | 572 | 2026-03-27 | 2026-06-26 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP25151 | NV Energy 2025 | 100% | Dom | #NAME? | #NAME? |  | #NAME? | #NAME? | 551 | 105 | 60 | 261 | 426 | 2025-12-08 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP26031 | Eversource 2026 | 0% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 170 | 850 |  | 1020 | 2026-08-07 | 2026-12-11 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMLP24118 | SSE SHET | 100% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 3597 | 300 | 632 | 893 | 1825 | 2025-12-08 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP25122 | NGUS S1 U2 Mapping | 100% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 16 | 8 | 20 | - | 28 | 2025-12-17 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMAP25108 | Powerlink CopperString | 100% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 61 | 45 | 60 | N/A | 105 | 2026-01-16 | 2026-05-22 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMAP26001 | Transgrid 2026 | 100% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 7023 | 2750 | 3500 | 512 | 6762 | 2026-01-30 | 2026-05-22 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP25119 | ComEd Wood to Steel | 100% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 181 | 80 | 140 | 64 | 284 | 2026-02-02 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP26011 | Xcel HB 2026 | 100% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 642 | 330 | 600 | N/A | 930 | 2026-02-02 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP25104-1 | Xcel W3419 | 100% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 8 |  | 8 |  | 8 | 2026-02-05 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP26009 | Ameren UAV Processing | 100% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 154 | 8 | 36 |  | 44 | 2026-02-06 | 2026-06-12 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMAP25126 | Powerlink MacIntyre | 100% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 52 | 40 | 20 | N/A | 60 | 2026-02-13 | 2026-05-01 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP25038 | Avangrid CMP Engr | 100% | Carlos | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 274 | 60 | 150 | 135 | 345 | 2025-10-24 | 2026-05-01 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP26019 | Xcel PSCo & SPS | 100% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 229 | 110 | 300 | N/A | 410 | 2026-03-09 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP26014 | LS Power Collinsville | 100% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 39 | 8 | 8 | N/A | 16 | 2026-03-23 |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMCP26037 | HONI DKPL2 | 100% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 8 | N/A | 8 | N/A | 8 | 2026-04-17 | 2026-05-01 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMCP230171 | HONI Patrol 2023 - Rework | 100% | Carlos | 1048.72 |  |  | #NAME? | #NAME? |  | -- | 40 | 144 | 184 |  | 2025-10-20 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMCP25032_1 | HONI 2025 PLS | 100% | Carlos | 719.81 | 191.67 |  |  |  |  | 65.04 | 242.94 | 526.77 | 834.75 |  |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | TRUE
NMIP26035 | ComEd CSX | 37% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 54 | 20 | 32 |  | 52 | 2026-06-12 | 2026-06-12 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP26038 | Lansing BWL 2026 | 0% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | [7 empty] | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP26041 | CMP Eng 2026 | 0% |  | #NAME? | #NAME? |  | #NAME? | #NAME? |  | 100 |  |  | 100 |  |  | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP23020 | FPL Spring Tx | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 321 | 582 | 828 | 1731 |  | 2023-08-31 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP23027 | LGE Spring 2023 (Tx) | 100% | Team 1 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 105 | 131 | 272 | 508 |  | 2023-06-27 |  |  |  | #REF! |  |  | #NAME? |  | TRUE
NMIP240141 | SoCo APC Vines and Dead Trees | 100% | Team 2 | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  |  | 300 | [7 empty] | #REF! |  |  | #NAME? |  | TRUE
NMIP26042 | PG&E M4 |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | N/A | N/A |  | 0 | 2026-07-10 | 2027-01-01 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP26043 | Xcel NSP Spring 2026 | 2% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 1647 | 670 | 940 | N/A | 1610 | 2026-05-22 | 2026-07-31 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP26044 | LGE Spring 2026 | 0% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? |  | 125 |  |  |  | 2026-08-21 | 2026-08-28 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP26055 | SoCo GPC 2026 | 0% |  | #NAME? | #NAME? |  | #NAME? | #NAME? | 2268 | 800 | 1770 | N/A | 2570 | 2026-06-05 | 2026-10-30 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMIP26056 | SoCo APC 2026 | 0% |  | #NAME? | #NAME? |  | #NAME? | #NAME? | 2099 | 800 | 1520 | N/A | 2320 | 2026-06-26 | 2026-10-30 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMLP25094 | SHET RIIO-T3 | 18% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 7321 | 450 | 800 | 4313 | 5563 | 2026-04-24 | 2026-12-18 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
NMLP26012 | WSP EDN2 | 0% |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | 66 | 30 | 65 | N/A | 95 | 2026-06-26 | 2026-06-26 | #NAME? | #NAME? | #NAME? | #REF! |  |  | #NAME? |  | FALSE
Project Awarded | [10 empty] | ` | [12 empty] | TRUE
Projects Awaiting PO/MSA | [23 empty] | TRUE
Processing Hours to be Reviewed | [23 empty] | TRUE
Note on K2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @seweryn.cieslik@nmgroup.com kye questions before update capacity. SOCO urgent/rapid veg start sometime between 10-16th. But is Main Build ok to start later on? Assigned to seweryn.cieslik@nmgroup.com
Note on Q2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @luke.beaumont@nmgroup.com can please provide dates for start Assigned to luke.beaumont@nmgroup.com
Note on R2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com please provide dates for the start Assigned to dominic.wilson@nmgroup.com
Note on K12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: wait on kickoff but maybe minimal merging exciting data form clusters in new AOI (then wait to see what happens with other half of data)
Note on L12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes creating and testing time for new attribution
Note on M24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @carlos.fuentes@nmgroup.com Assigned to carlos.fuentes@nmgroup.com Reply: @carlos.fuentes@nmgroup.com Is this 2,025 total the real estimate now? I know the bid model might not be right, but that was less than 900 hours Reply: as mentioned. the expected rate is 40km/day plus formatting which amasses to the estimate provided by Carlos
Note on K25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @luke.beaumont@nmgroup.com checking with olivia if ortho easier to ask subcon update ortho from exciting subcon work
Note on K26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Does not include any rapid veg hours yet - need to know % scope for this
Note on L26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com how did you came up with this number? Assigned to dominic.wilson@nmgroup.com Reply: This was the total hours from the estimates, I have now removed and combined a few workflows, and improved my estimates to bring this number down Reply: I did a comparison with 2025 actuals - 5000 h seems reasonable taking into account ROW tripled
Note on M26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This include "Preparation-Review bak files coverage" time and PLS offset Reports - Once we know better the extension of the Additions, we will update this number Reply: not sure if this is not too optimistic Reply: I will review tomorrow with Matt and Darren
Note on K32: Includes FLI and Obliques
Note on K39: Includes Obliques
Note on K42: Include FLI
Note on L61: +714 hours from the plan
Note on M61: +585 hours from the plan
Note on L73: +275 hours from the plan
Note on D77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @luke.beaumont@nmgroup.com can you hyperlink project codes with the trackers that you maintain for each of your projects, thanks Assigned to luke.beaumont@nmgroup.com
Note on L82: +124 hours from the plan
Note on M82: +217 hours from the plan
Note on L88: +75 hours from the plan
Note on M88: +54 hours from the plan
Note on D105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com can you hyperlink project codes with the trackers that you maintain for each of your projects, thanks Assigned to dominic.wilson@nmgroup.com
Note on D107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @carlos.fuentes@nmgroup.com can you hyperlink project codes with the trackers that you maintain for each of your projects, thanks Assigned to carlos.fuentes@nmgroup.com
Note on M109: Updated PLS model rates from 12 Km/day (PLS Model + Temp Calcs = 340 h) to 7 Km/day
Note on D114: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @carlos.fuentes@nmgroup.com Assigned to carlos.fuentes@nmgroup.com
Note on B117: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @dominic.wilson@nmgroup.com this is not a project tracker
Note on B119: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DoT
Note on B121: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DoT? Reply: @luke.beaumont@nmgroup.com
Note on L121: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com Assigned to dominic.wilson@nmgroup.com
Note on B122: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @luke.beaumont@nmgroup.com DoT?
Note on K124: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @luke.beaumont@nmgroup.com Assigned to luke.beaumont@nmgroup.com
Note on L124: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com Assigned to dominic.wilson@nmgroup.com
Note on E125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @jorge.rodriguez@nmgroup.com these number come from a projects Tracker? 475 and 262 are the miles distances? Assigned to jorge.rodriguez@nmgroup.com Reply: Hi Luke, distances were in miles in the Projects tracker. This is now fixed. Thank you
Note on L125: removed resources off FLi in capacity plan but kept the hours in GIS in favour for Xcel
Note on M125: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @carlos.fuentes@nmgroup.com Assigned to carlos.fuentes@nmgroup.com Reply: PLS CADD Model (M4/M1) 818 hrs + Temp Calcs 64 hrs + Setup Time 147 hrs = 1029 hrs
Note on L126: Just Class
Note on M126: Model+TC+FLI
Note on B128: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com data has been handed over. Please work with Olivia to get it subcontracted for classification Assigned to dominic.wilson@nmgroup.com
Note on K129: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @luke.beaumont@nmgroup.com you should add 49 hr for FLI here Assigned to luke.beaumont@nmgroup.com
Note on M129: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3D Topographic Vectors 20 Km/day+ PLS CADD Model 10 Km/day + Caydence Outputs 16hrs + Temperature Calculations 80 Km/day + Clearance Report 44 Km/day + (Minimum Time 182 hrs) = 289 h
Note on O129: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @luke.beaumont@nmgroup.com Hi Luke could you just confirm for me if this is still the expected start date for RS? Just as I won't bother with the tech specs just yet if so! Assigned to luke.beaumont@nmgroup.com
Note on B130: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com Assigned to dominic.wilson@nmgroup.com
Note on K131: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @luke.beaumont@nmgroup.com Assigned to luke.beaumont@nmgroup.com
Note on L131: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com Assigned to dominic.wilson@nmgroup.com
Note on M131: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @carlos.fuentes@nmgroup.com Assigned to carlos.fuentes@nmgroup.com
Note on K132: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @luke.beaumont@nmgroup.com Assigned to luke.beaumont@nmgroup.com Reply: +cont obliques?
Note on L132: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com Assigned to dominic.wilson@nmgroup.com
Note on M132: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @carlos.fuentes@nmgroup.com Assigned to carlos.fuentes@nmgroup.com
Note on K133: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @luke.beaumont@nmgroup.com check if going through FLOW and partly processed in OPS do i need full hours here or reduce? Assigned to luke.beaumont@nmgroup.com
Note on L133: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com Assigned to dominic.wilson@nmgroup.com
Note on K134: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @luke.beaumont@nmgroup.com
Note on L134: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @dominic.wilson@nmgroup.com
Note on M134: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @carlos.fuentes@nmgroup.com
Note on M135: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @carlos.fuentes@nmgroup.com Assigned to carlos.fuentes@nmgroup.com
Note on K136: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: seem too high @luke.beaumont@nmgroup.com Assigned to luke.beaumont@nmgroup.com
Note on K137: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @luke.beaumont@nmgroup.com
Note on L137: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @dominic.wilson@nmgroup.com
Note on M137: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @carlos.fuentes@nmgroup.com Assigned to carlos.fuentes@nmgroup.com
Note on B140: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need upadte list for double circuits meringue as one
Note on K140: full scope 750h
Note on L140: 1200h based on the full scope
Note on M140: 3858h based on the full scope
Note on M142: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @carlos.fuentes@nmgroup.com Assigned to carlos.fuentes@nmgroup.com
Note on K143: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: -150 hours form execeted PLS support on orthos. Ortho rates toi be review but likely some more horus will be reduced
Note on M143: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @carlos.fuentes@nmgroup.com Assigned to carlos.fuentes@nmgroup.com Reply: PLS Offset Report 750 Km/day (134 hr) + Client PLS CADD Wrangling 1250 Km/day (80 hr) + UAT 16hr + Training 24hr + (Minimum Time 257 hrs) = 512 hrs
Note on L144: includes Obliques
Note on M144: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @carlos.fuentes@nmgroup.com Assigned to carlos.fuentes@nmgroup.com Reply: PLS CADD Import 16 hrs+ Processed Weather Data 12 hrs + Setup Time 36 hrs = 64 h
Note on K145: inlcudes EO/footprints but not cont obliques
Note on K147: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @seweryn.cieslik@nmgroup.com this depends on how we are expectoing data to arrive. The email said Toiled Point cloud so if more of a immediate QC. Mihai spoke before about setting up infrastructure on UAV projects differently to normal capture. Lete me know if he will take a lead here or set up a new flow and i can provide resources where needed. Reply: have asked Jorge as well but he is away until Monday and that if similar to nmip25109
Note on K155: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @luke.beaumont@nmgroup.com
Note on L155: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @dominic.wilson@nmgroup.com
Note on K157: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @luke.beaumont@nmgroup.com Assigned to luke.beaumont@nmgroup.com
Note on L157: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com Assigned to dominic.wilson@nmgroup.com
Note on M157: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @carlos.fuentes@nmgroup.com Assigned to carlos.fuentes@nmgroup.com
Note on K162: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Original 500 brought obliques/ raw point cloud + original estimates based on 1800 row
Note on B163: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @seweryn.cieslik@nmgroup.com NMIP26008 CMP VEGS 2026 added? Will put some horus to FLOW/FLAI fo this project vectoritaion for rapidveg workflow? Assigned to seweryn.cieslik@nmgroup.com
Note on K163: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @luke.beaumont@nmgroup.com Assigned to luke.beaumont@nmgroup.com Reply: + cont obliques?
Note on L163: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com Assigned to dominic.wilson@nmgroup.com
Note on M163: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @carlos.fuentes@nmgroup.com Assigned to carlos.fuentes@nmgroup.com
Note on K164: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assume had extra effort for new rveg request + any urgent that need adding on
Note on L164: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com is this includes Obliques hours? Assigned to dominic.wilson@nmgroup.com Reply: Yeh both APC and GPC hours include Oblique Processing and QC Reply: How many hours then for both projects allocated to obliques? Reply: 560 hours based on 100km/day combined for both projects
Note on K165: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: assume r veg needed in RS. Mark alluded to Keirene that Ops would need support on Urgent infringemtns effort linked Add on 1/2 Urgent effort?
Note on M166: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PLS CADD Model 1860 hrs + Clearance Schedule 279 hrs + (Developed Oblique Imagery 528 hrs Full SOW + Georeferenced Video 369 hrs Full SOW) + Line Schedule 372 hrsy +(Minimum Time 904 hrs) = 4313 hrs
Note on K167: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need more info, before this is final

## Roster Daily
Name | Team | Primary Role | Secondary Role | time axis 2025-06-30 to 2027-12-31
Brown, Ben | 1_RS | Remote Sensing Processor | GIS Technician | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Glen-Findlay, Annie | 1_RS | Remote Sensing Technician |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | BH | 8 | 8 | 8 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Kucharczyk, Wojciech | 1_RS | Remote Sensing Processor |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Lau, Zara | 1_RS | Remote Sensing Technician |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Mulero, Alberto | 1_RS | Remote Sensing Processor | GIS Technician | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Murphy, Keiren | 1_RS | Remote Sensing Technician |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Phillpotts, Gregory | 1_RS | Remote Sensing Technician |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | BH | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
Skarbek, Andrzej | 1_RS | Remote Sensing Processor | GIS Technician | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | BH | BH | 0 | 0 | 0 | BH | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Bernadic, Jakub | 1_RS | Remote Sensing Processor | [6 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 8 | 8 | 8 | 8 | 8 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Alvarez, Maria | 1_RS | Remote Sensing Technician |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 0 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 0 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Allott, Mathew | 2_GIS | GIS Technician |  | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Ditcher, Steven | 2_GIS | Geospatial Processor |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | BH | 0 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Balmforth, Chloe | 2_GIS | GIS Technician |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dunhill, Rachel | 2_GIS | GIS Specialist |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Dyer, Rohan | 2_GIS | Geospatial Processor |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Limmer, David | 2_GIS | Geospatial Processor |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | BH | 0 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | BH | 0 | 0 | 0 | BH | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Handley-Watson, James | 2_GIS | GIS Technician |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 3.75 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | BH | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 4 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 4 | 0 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
Keelty, Victoria | 2_GIS | Geospatial Processor |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Keter, Titus | 2_GIS | Geospatial Processor |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | BH | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
King, Katie | 2_GIS | GIS Technician |  | 0 | 4 | 8 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Lander, Lauren | 2_GIS | Geospatial Processor |  | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | BH | BH | 0 | 0 | 0 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Mapley, Neil | 2_GIS | GIS Specialist |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | BH | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Mckay, Matthew | 2_GIS | GIS Technician |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
O'Connell, Luke | 2_GIS | Geospatial Processor |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | BH | 0 | 0 | 0 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Pena, Bethania | 2_GIS | Geospatial Processor |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Postgate, Emilie | 2_GIS | Geospatial Processor |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Rawling, Alice | 2_GIS | GIS Specialist |  | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 0 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 4 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Skrzypczynski, Filip | 2_GIS | GIS Technician |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | BH | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Webster, Joanne | 2_GIS | Geospatial Processor | [75 empty] | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 |  |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | [6 empty] | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | [5 empty] | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
Schuler, Felix | 3_PLS | Geospatial Processor |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | BH | 0 | 0 | 0 | BH |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Bell, Darren | 3_PLS | PLS-CADD Specialist |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Birkin, Chris | 3_PLS | PLS Processor | Geospatial Processor | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 8 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Hope, Matthew | 3_PLS | PLS Processor | Remote Sensing Processor | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | BH | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
Hunter, Alex | 3_PLS | PLS Technician |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | BH | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 3.75 | 0 | 0 | 3.75 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 7.5 | 7.5 | 7.5 | 3.75 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
Kidd, Lewis | 3_PLS | PLS Processor |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | BH | BH | 8 | 8 | 8 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Obora, Gregory | 3_PLS | PLS Processor |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | BH | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
Pointon, James | 3_PLS | PLS Processor | Remote Sensing Technician | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | BH | BH | 0 | 0 | 0 | BH | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Smythe, Gee | 3_PLS | PLS Technician |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Waterson, Kieron | 3_PLS | PLS-CADD Specialist |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | BH | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | BH | BH | 0 | 0 | 0 | BH | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 3.75 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
Woznica, Tomasz | 3_PLS | Geospatial Processor |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | BH | BH | 0 | 0 | 0 | BH |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Wolage, Robert | 3_PLS | PLS-CADD Specialist |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | BH | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | BH | BH | 0 | 0 | 0 | BH | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 7.5 | 7.5 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 0 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 0 | 0 | 7.5 | 7.5 | 7.5 | 0 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
[393 empty] | 0 | 0 |  |  |  | 0
[393 empty] | 0 | 0 |  |  |  | 0
Mumford, Mark | 2_GIS | PIT Specialist |  | 2025-08-11: 3; 2025-08-25: BH; 2025-09-08: 8; 2025-09-09: 8; 2025-09-10: 8; 2025-09-11: 8; 2025-09-12: 8; 2025-09-15: 8; 2025-09-16: 8; 2025-09-17: 8; 2025-09-18: 8; 2025-09-19: 8; 2025-09-22: 8; 2025-09-23: 8; 2025-09-24: 8; 2025-09-25: 8; 2025-09-26: 8; 2025-10-27: 8; 2025-10-28: 8; 2025-10-29: 8; 2025-11-03: 8; 2025-11-04: 8; 2025-11-05: 8; 2025-11-06: 8; 2025-11-07: 8; 2025-11-11: 8; 2025-11-12: 8; 2025-11-13: 8; 2025-11-14: 0; 2025-11-17: 8; 2025-11-18: 8; 2025-11-19: 8; 2025-11-20: 8; 2025-11-21: 8; 2025-11-24: 8; 2025-11-25: 8; 2025-11-26: 8; 2025-11-27: 8; 2025-11-28: 8; 2025-12-01: 8; 2025-12-02: 8; 2025-12-03: 8; 2025-12-04: 8; 2025-12-05: 8; 2025-12-25: BH; 2025-12-26: BH; 2026-01-01: BH; 2026-12-25: 0; 2026-12-28: 0; 2027-01-01: 0
Beznea, Mihai |  | PIT Specialist |  | 2025-08-25: BH; 2025-11-03: 8; 2025-11-04: 8; 2025-11-05: 8; 2025-11-06: 8; 2025-11-07: 8; 2025-11-10: 8; 2025-11-11: 8; 2025-11-12: 8; 2025-11-13: 8; 2025-11-14: 8; 2025-12-25: BH; 2025-12-26: BH; 2026-01-01: BH; 2026-12-25: 0; 2026-12-28: 0; 2027-01-01: 0
Birkin, Chris | 2_GIS |  |  | 2025-08-27: 8; 2025-08-28: 8; 2025-12-25: BH; 2025-12-26: BH; 2026-01-01: BH; 2026-06-04: 8; 2026-06-05: 8; 2026-06-08: 8; 2026-06-09: 8; 2026-06-10: 8; 2026-06-11: 8; 2026-06-12: 8; 2026-06-15: 8; 2026-06-16: 8; 2026-06-17: 8; 2026-06-18: 8; 2026-06-19: 8; 2026-06-22: 8; 2026-06-23: 8; 2026-06-24: 8; 2026-06-25: 8; 2026-06-26: 8; 2026-06-29: 8; 2026-06-30: 8; 2026-07-01: 8; 2026-07-02: 8; 2026-07-03: 8; 2026-12-25: 0; 2026-12-28: 0; 2027-01-01: 0
Pointon, James | 2_GIS |  |  | 2025-12-25: BH; 2025-12-26: BH; 2026-01-01: BH; 2026-06-08: 8; 2026-06-09: 8; 2026-06-10: 8; 2026-06-11: 8; 2026-06-12: 8; 2026-06-15: 8; 2026-06-16: 8; 2026-06-17: 8; 2026-06-29: 8; 2026-06-30: 8; 2026-07-01: 8; 2026-07-02: 8; 2026-07-03: 8; 2026-12-25: 0; 2026-12-28: 0; 2027-01-01: 0
Brown, Ben | 2_GIS |  |  | 2025-12-25: BH; 2025-12-26: BH; 2026-01-01: BH; 2026-06-17: 8; 2026-06-18: 8; 2026-06-19: 8; 2026-06-22: 8; 2026-06-23: 8; 2026-06-24: 8; 2026-06-25: 8; 2026-06-26: 8; 2026-06-29: 8; 2026-06-30: 8; 2026-07-01: 8; 2026-07-02: 8; 2026-07-03: 8; 2026-12-25: 0; 2026-12-28: 0; 2027-01-01: 0
Mulero, Alberto | 2_GIS |  |  | 2025-12-25: BH; 2025-12-26: BH; 2026-01-01: BH; 2026-06-23: 8; 2026-06-24: 8; 2026-06-25: 8; 2026-06-26: 8; 2026-06-29: 8; 2026-06-30: 8; 2026-07-01: 8; 2026-07-02: 8; 2026-07-03: 8; 2026-12-25: 0; 2026-12-28: 0; 2027-01-01: 0
Skarbek, Andrzej | 2_GIS | bar: 2025-12-25 to 2025-12-26; 2026-01-01
Shires, Charles | 3_PLS |  |  | 2025-08-25: 0; 2025-11-24: 8; 2025-11-25: 8; 2025-11-26: 8; 2025-11-27: 8; 2025-11-28: 8; 2025-12-01: 8; 2025-12-02: 8; 2025-12-03: 8; 2025-12-04: 8; 2025-12-05: 8; 2025-12-08: 8; 2025-12-09: 8; 2025-12-10: 8; 2025-12-11: 8; 2025-12-12: 8; 2025-12-15: 8; 2025-12-16: 8; 2025-12-17: 8; 2025-12-25: BH; 2025-12-26: BH; 2026-01-01: BH
[132 empty] | BH | BH |  |  |  | BH
[132 empty] | BH | BH |  |  |  | BH
[132 empty] | BH | BH |  |  |  | BH
[132 empty] | BH | BH |  |  |  | BH
[132 empty] | BH | BH |  |  |  | BH
[132 empty] | BH | BH |  |  |  | BH
| RS |  | RS | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 71.5 | 71.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 55.5 | 55.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 55.5 | 0 | 63.5 | 71.5 | 71.5 | 71.5 | 64 | 64 | 71.5 | 71.5 | 71.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 55.5 | 55.5 | 55.5 | 55.5 | 63.5 | 55.5 | 63.5 | 63.5 | 63.5 | 63.5 | 55.5 | 63.5 | 63.5 | 55.5 | 47.5 | 55.5 | 47.5 | 47.5 | 55.5 | 55.5 | 48 | 55.5 | 55.5 | 63.5 | 63.5 | 63.5 | 47.5 | 47.5 | 47.5 | 55.5 | 55.5 | 55.5 | 55.5 | 63.5 | 63.5 | 55.5 | 55.5 | 55.5 | 64 | 64 | 64 | 64 | 64 | 71.5 | 63.5 | 63.5 | 63.5 | 63.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 63.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 64 | 64 | 64 | 24 | 24 | 12 | 0 | 0 | 8 | 8 | 8 | 0 | 16 | 56 | 56 | 63.5 | 63.5 | 63.5 | 67.5 | 71.5 | 63.5 | 63.5 | 63.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 63.5 | 63.5 | 63.5 | 47.5 | 47.5 | 71.5 | 71.5 | 71.5 | 71.5 | 63.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 79.5 | 79.5 | 79.5 | 71.5 | 71.5 | 79.5 | 79.5 | 79.5 | 71.5 | 79.5 | 71.5 | 79.5 | 79.5 | 71.5 | 79.5 | 79.5 | 79.5 | 79.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 63.5 | 79.5 | 79.5 | 79.5 | 63.5 | 59.5 | 55.5 | 63.5 | 63.5 | 48 | 0 | 0 | 72 | 72 | 72 | 56 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 63.5 | 71.5 | 71.5 | 63.5 | 79.5 | 79.5 | 79.5 | 79.5 | 71.5 | 0 | 79.5 | 79.5 | 79.5 | 79.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 63.5 | 71.5 | 71.5 | 71.5 | 0 | 71.5 | 71.5 | 71.5 | 71.5 | 63.5 | 71.5 | 71.5 | 71.5 | 63.5 | 63.5 | 63.5 | 63.5 | 55.5 | 59.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 55.5 | 55.5 | 55.5 | 55.5 | 55.5 | 55.5 | 55.5 | 55.5 | 55.5 | 55.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 71.5 | 79.5 | 79.5 | 79.5 | 79.5 | 71.5 | 71.5 | 71.5 | 71.5 | 79.5 | 71.5 | 71.5 | 71.5 | 71.5 | 71.5 | 0 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 63.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 0 | 0 | 79.5 | 79.5 | 79.5 | 0 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5 | 79.5
| GIS |  | GIS | 125.5 | 113.5 | 125.5 | 121.5 | 125.5 | 109.5 | 109.5 | 102 | 102 | 94 | 109.5 | 125 | 125 | 125 | 117 | 117 | 121.25 | 125 | 125 | 117.5 | 133 | 133 | 133 | 133 | 125 | 117 | 133 | 133 | 133 | 125.5 | 128 | 133 | 133 | 125 | 125 | 117.5 | 117.5 | 125 | 117 | 102 | 0 | 94 | 117 | 125 | 109.5 | 110.5 | 110.5 | 110.5 | 102.5 | 102.5 | 134 | 134 | 134 | 134 | 134 | 126 | 126 | 134 | 134 | 126 | 118 | 126 | 134 | 118.5 | 118.5 | 119 | 134 | 134 | 134 | 134 | 134 | 130 | 126 | 118.5 | 126 | 134 | 134 | 134 | 134 | 126 | 141.5 | 141.5 | 141.5 | 133.5 | 133.5 | 141.5 | 141.5 | 141.5 | 118 | 126 | 126.5 | 134 | 134 | 134 | 134 | 126 | 134 | 134 | 134 | 126 | 134 | 134 | 134 | 134 | 118.5 | 111 | 134.5 | 134.5 | 134.5 | 134.5 | 142 | 142 | 138.5 | 142 | 142 | 118.5 | 110.5 | 102.5 | 110.5 | 102.5 | 118 | 118 | 118 | 118 | 118 | 32 | 28 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 39.5 | 102.5 | 102.5 | 110.5 | 102.5 | 102.5 | 95 | 106 | 118 | 126 | 122.5 | 126.5 | 134 | 134 | 126.5 | 118.5 | 126 | 134 | 126.5 | 134 | 110 | 126.5 | 126.5 | 127 | 119 | 111 | 127 | 127 | 127 | 127 | 127 | 119 | 127 | 127 | 127 | 127 | 119.5 | 119.5 | 127 | 111.5 | 103.5 | 111 | 111.5 | 107.5 | 111.5 | 107.5 | 107 | 111 | 111 | 111 | 111 | 119 | 119 | 127 | 127 | 134.5 | 134.5 | 134.5 | 126.5 | 134.5 | 119 | 119 | 134.5 | 134.5 | 134.5 | 0 | 0 | 119 | 119 | 127 | 111 | 107 | 111.5 | 111.5 | 111.5 | 119 | 135 | 135 | 135 | 135 | 119 | 135 | 119 | 135 | 135 | 127.5 | 0 | 131 | 135 | 135 | 135 | 123 | 135 | 135 | 135 | 119 | 123.5 | 135 | 135 | 135 | 127 | 0 | 119 | 119 | 111.5 | 95.5 | 103 | 111 | 111 | 119 | 119 | 127 | 127 | 119 | 111 | 119 | 135 | 127 | 127 | 127 | 119 | 127 | 135 | 135 | 135 | 135 | 151 | 159 | 159 | 159 | 151 | 119 | 119 | 111 | 111 | 111 | 103 | 103 | 103 | 103 | 111 | 119 | 119 | 111 | 111 | 111 | 111 | 111 | 111 | 103 | 95 | 95 | 111 | 119 | 119 | 111.5 | 111.5 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 119 | 119 | 119 | 119 | 111.5 | 0 | 119 | 127 | 127 | 127 | 119.5 | 119.5 | 119.5 | 119.5 | 119.5 | 127 | 119 | 119 | 111.5 | 119 | 111 | 111 | 111 | 111 | 111 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 119 | 119 | 119 | 119 | 127 | 127 | 127 | 127 | 127 | 119.5 | 119.5 | 119.5 | 119.5 | 119.5 | 119.5 | 119.5 | 119.5 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 119 | 119 | 119 | 119 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 0 | 0 | 127 | 127 | 127 | 0 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127
| PLS |  | PLS | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 78.5 | 93.5 | 89.5 | 86 | 86 | 86 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 85.5 | 85.5 | 85.5 | 85.5 | 78 | 70.5 | 93.5 | 93.5 | 93.5 | 93.5 | 78 | 62.5 | 85.5 | 85.5 | 85.5 | 77.5 | 77.5 | 85.5 | 85.5 | 93.5 | 93.5 | 0 | 86 | 78 | 78 | 86 | 93.5 | 85.5 | 85.5 | 93.5 | 86 | 86 | 78 | 93.5 | 93.5 | 89.5 | 77.5 | 77.5 | 85.5 | 85.5 | 77.5 | 39 | 70 | 70 | 70 | 70 | 85.5 | 85.5 | 81.5 | 85.5 | 85.5 | 78.5 | 70.5 | 70 | 69.5 | 77.5 | 77.5 | 77.5 | 77.5 | 77.5 | 73.75 | 70 | 70 | 73.75 | 77.5 | 77.5 | 62 | 69.5 | 69.5 | 69.5 | 61.5 | 85.5 | 93.5 | 93.5 | 93.5 | 93.5 | 86 | 93.5 | 93.5 | 93.5 | 93.5 | 85.5 | 85.5 | 85.5 | 78 | 78 | 79 | 79 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 86 | 78 | 93.5 | 94 | 101.5 | 78.5 | 93.5 | 86 | 77.5 | 70 | 31.5 | 31.5 | 31.5 | 0 | 0 | 8 | 8 | 8 | 0 | 24 | 78 | 78 | 78 | 74.25 | 70.5 | 86 | 93.5 | 93.5 | 93.5 | 93.5 | 78 | 93.5 | 93.5 | 93.5 | 85.5 | 86 | 93.5 | 93.5 | 85.5 | 77.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 86 | 86 | 78.5 | 78.5 | 71 | 78.5 | 86 | 70 | 78 | 86 | 86 | 86 | 86 | 86 | 78 | 82 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 85.5 | 86 | 86 | 86 | 93.5 | 93.5 | 85.5 | 93.5 | 0 | 0 | 86 | 86 | 93.5 | 85.5 | 78 | 86 | 86 | 78 | 78 | 70.5 | 85.5 | 93.5 | 93.5 | 85.5 | 78 | 78 | 86 | 93.5 | 93.5 | 0 | 86 | 86 | 85.5 | 77.5 | 85.5 | 81.75 | 85.5 | 77.5 | 77.5 | 85.5 | 86 | 86 | 78 | 70 | 0 | 70.5 | 78 | 78 | 62 | 78 | 78 | 78 | 93.5 | 78 | 78 | 78 | 70 | 62 | 69.5 | 69.5 | 69.5 | 69.5 | 70 | 67.5 | 85.5 | 85.5 | 85.5 | 85.5 | 85.5 | 77.5 | 77.5 | 77.5 | 77.5 | 77.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 85.5 | 85.5 | 85.5 | 85.5 | 78 | 85.5 | 93.5 | 93.5 | 86 | 86 | 86 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 86 | 78.5 | 78.5 | 78.5 | 86 | 86 | 86 | 93.5 | 93.5 | 93.5 | 78 | 78 | 86 | 93.5 | 85.5 | 77.5 | 70 | 0 | 86 | 86 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 85.5 | 85.5 | 85.5 | 85.5 | 85.5 | 85.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 85.5 | 0 | 0 | 93.5 | 93.5 | 93.5 | 0 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5
| TOTAL |  | TOTAL | 282.5 | 270.5 | 282.5 | 278.5 | 282.5 | 259.5 | 274.5 | 255 | 251.5 | 243.5 | 259 | 282 | 282 | 274 | 266 | 274 | 278.25 | 282 | 282 | 266.5 | 290 | 290 | 290 | 282.5 | 267 | 282 | 298 | 298 | 290 | 267 | 254 | 282 | 282 | 274 | 266 | 258.5 | 266.5 | 274 | 274 | 251 | 0 | 243.5 | 266.5 | 274.5 | 267 | 268 | 260 | 267.5 | 267.5 | 260 | 283.5 | 275.5 | 291 | 291 | 287 | 267 | 267 | 275 | 275 | 259 | 212.5 | 259.5 | 259.5 | 252 | 252 | 268 | 283 | 271 | 283 | 283 | 268 | 248 | 251.5 | 235.5 | 251 | 267 | 267 | 259.5 | 267 | 255.25 | 275 | 275 | 278.75 | 258.5 | 258.5 | 251 | 266.5 | 266.5 | 243 | 243 | 275.5 | 291 | 283 | 283 | 283 | 276 | 291.5 | 291.5 | 291.5 | 283.5 | 291 | 283 | 283 | 275.5 | 260 | 261.5 | 285 | 300 | 300 | 300 | 307.5 | 307.5 | 304 | 307.5 | 307.5 | 276 | 252 | 267.5 | 276 | 275.5 | 268 | 283 | 268 | 259.5 | 252 | 87.5 | 83.5 | 59.5 | 0 | 0 | 16 | 16 | 16 | 0 | 79.5 | 236.5 | 236.5 | 252 | 240.25 | 236.5 | 248.5 | 271 | 275 | 283 | 279.5 | 276 | 299 | 299 | 291.5 | 275.5 | 275.5 | 291 | 283.5 | 267 | 235 | 291.5 | 291.5 | 292 | 284 | 268 | 284.5 | 284.5 | 277 | 277 | 269.5 | 277 | 292.5 | 276.5 | 276.5 | 284.5 | 285 | 285 | 292.5 | 269 | 261 | 264.5 | 284.5 | 280.5 | 276.5 | 280.5 | 280 | 284 | 284 | 276 | 276 | 284 | 284 | 292 | 292 | 291.5 | 307.5 | 299.5 | 292 | 284 | 264.5 | 268 | 291.5 | 283.5 | 276 | 0 | 0 | 277 | 277 | 292.5 | 252.5 | 256.5 | 269 | 269 | 261 | 268.5 | 277 | 284 | 300 | 300 | 268 | 292.5 | 276.5 | 300.5 | 308 | 292.5 | 0 | 296.5 | 300.5 | 300 | 292 | 280 | 288.25 | 292 | 284 | 268 | 280.5 | 284.5 | 292.5 | 284.5 | 268.5 | 0 | 261 | 268.5 | 261 | 229 | 244.5 | 260.5 | 260.5 | 284 | 260.5 | 268.5 | 268.5 | 252.5 | 228.5 | 248 | 268 | 260 | 260 | 260.5 | 250 | 268 | 276 | 276 | 276 | 276 | 284 | 292 | 292 | 292 | 284 | 276 | 276 | 268 | 268 | 268 | 260 | 260 | 260 | 260 | 260.5 | 276 | 284 | 276 | 268.5 | 268.5 | 268.5 | 276 | 276 | 268 | 260 | 268 | 284 | 292 | 284.5 | 269.5 | 261.5 | 285 | 292.5 | 292.5 | 292.5 | 292 | 292 | 292 | 276.5 | 284.5 | 276.5 | 284 | 276 | 268 | 253 | 0 | 268.5 | 276.5 | 284 | 284 | 276.5 | 276.5 | 276.5 | 276.5 | 276.5 | 284 | 276 | 292 | 284.5 | 292 | 284 | 284 | 284 | 284 | 284 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 292 | 292 | 292 | 292 | 300 | 300 | 300 | 300 | 300 | 292.5 | 292.5 | 292.5 | 292.5 | 292.5 | 292.5 | 292.5 | 284.5 | 292 | 292 | 292 | 292 | 292 | 300 | 300 | 300 | 300 | 292 | 292 | 292 | 292 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 292 | 0 | 0 | 300 | 300 | 300 | 0 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300
Note on JE6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @luke.beaumont@nmgroup.com @dominic.wilson@nmgroup.com RS to GIS date? Reply: when you agree. zero his RS hours and move them to row 50 please Reply: from 23/6 to 31/7
Note on IK32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Off-sick

## Allocation Daily
Name | Team | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-29 | 2026-06-30 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31 | 2027-01-01 | 2027-01-04 | 2027-01-05 | 2027-01-06 | 2027-01-07 | 2027-01-08 | 2027-01-11 | 2027-01-12 | 2027-01-13 | 2027-01-14 | 2027-01-15 | 2027-01-18 | 2027-01-19 | 2027-01-20 | 2027-01-21 | 2027-01-22 | 2027-01-25 | 2027-01-26 | 2027-01-27 | 2027-01-28 | 2027-01-29 | 2027-02-01 | 2027-02-02 | 2027-02-03 | 2027-02-04 | 2027-02-05 | 2027-02-08 | 2027-02-09 | 2027-02-10 | 2027-02-11 | 2027-02-12 | 2027-02-15 | 2027-02-16 | 2027-02-17 | 2027-02-18 | 2027-02-19 | 2027-02-22 | 2027-02-23 | 2027-02-24 | 2027-02-25 | 2027-02-26 | 2027-03-01 | 2027-03-02 | 2027-03-03 | 2027-03-04 | 2027-03-05 | 2027-03-08 | 2027-03-09 | 2027-03-10 | 2027-03-11 | 2027-03-12 | 2027-03-15 | 2027-03-16 | 2027-03-17 | 2027-03-18 | 2027-03-19 | 2027-03-22 | 2027-03-23 | 2027-03-24 | 2027-03-25 | 2027-03-26 | 2027-03-29 | 2027-03-30 | 2027-03-31 | 2027-04-01 | 2027-04-02 | 2027-04-05 | 2027-04-06 | 2027-04-07 | 2027-04-08 | 2027-04-09 | 2027-04-12 | 2027-04-13 | 2027-04-14 | 2027-04-15 | 2027-04-16 | 2027-04-19 | 2027-04-20 | 2027-04-21 | 2027-04-22 | 2027-04-23 | 2027-04-26 | 2027-04-27 | 2027-04-28 | 2027-04-29 | 2027-04-30 | 2027-05-03 | 2027-05-04 | 2027-05-05 | 2027-05-06 | 2027-05-07 | 2027-05-10 | 2027-05-11 | 2027-05-12 | 2027-05-13 | 2027-05-14 | 2027-05-17 | 2027-05-18 | 2027-05-19 | 2027-05-20 | 2027-05-21 | 2027-05-24 | 2027-05-25 | 2027-05-26 | 2027-05-27 | 2027-05-28 | 2027-05-31 | 2027-06-01 | 2027-06-02 | 2027-06-03 | 2027-06-04 | 2027-06-07 | 2027-06-08 | 2027-06-09 | 2027-06-10 | 2027-06-11 | 2027-06-14 | 2027-06-15 | 2027-06-16 | 2027-06-17 | 2027-06-18 | 2027-06-21 | 2027-06-22 | 2027-06-23 | 2027-06-24 | 2027-06-25 | 2027-06-28 | 2027-06-29 | 2027-06-30 | 2027-07-01 | 2027-07-02 | 2027-07-05 | 2027-07-06 | 2027-07-07 | 2027-07-08 | 2027-07-09 | 2027-07-12 | 2027-07-13 | 2027-07-14 | 2027-07-15 | 2027-07-16 | 2027-07-19 | 2027-07-20 | 2027-07-21 | 2027-07-22 | 2027-07-23 | 2027-07-26 | 2027-07-27 | 2027-07-28 | 2027-07-29 | 2027-07-30 | 2027-08-02 | 2027-08-03 | 2027-08-04 | 2027-08-05 | 2027-08-06 | 2027-08-09 | 2027-08-10 | 2027-08-11 | 2027-08-12 | 2027-08-13 | 2027-08-16 | 2027-08-17 | 2027-08-18 | 2027-08-19 | 2027-08-20 | 2027-08-23 | 2027-08-24 | 2027-08-25 | 2027-08-26 | 2027-08-27 | 2027-08-30 | 2027-08-31 | 2027-09-01 | 2027-09-02 | 2027-09-03 | 2027-09-06 | 2027-09-07 | 2027-09-08 | 2027-09-09 | 2027-09-10 | 2027-09-13 | 2027-09-14 | 2027-09-15 | 2027-09-16 | 2027-09-17 | 2027-09-20 | 2027-09-21 | 2027-09-22 | 2027-09-23 | 2027-09-24 | 2027-09-27 | 2027-09-28 | 2027-09-29 | 2027-09-30 | 2027-10-01 | 2027-10-04 | 2027-10-05 | 2027-10-06 | 2027-10-07 | 2027-10-08 | 2027-10-11 | 2027-10-12 | 2027-10-13 | 2027-10-14 | 2027-10-15 | 2027-10-18 | 2027-10-19 | 2027-10-20 | 2027-10-21 | 2027-10-22 | 2027-10-25 | 2027-10-26 | 2027-10-27 | 2027-10-28 | 2027-10-29 | 2027-11-01 | 2027-11-02 | 2027-11-03 | 2027-11-04 | 2027-11-05 | 2027-11-08 | 2027-11-09 | 2027-11-10 | 2027-11-11 | 2027-11-12 | 2027-11-15 | 2027-11-16 | 2027-11-17 | 2027-11-18 | 2027-11-19 | 2027-11-22 | 2027-11-23 | 2027-11-24 | 2027-11-25 | 2027-11-26 | 2027-11-29 | 2027-11-30 | 2027-12-01 | 2027-12-02 | 2027-12-03 | 2027-12-06 | 2027-12-07 | 2027-12-08 | 2027-12-09 | 2027-12-10 | 2027-12-13 | 2027-12-14 | 2027-12-15 | 2027-12-16 | 2027-12-17 | 2027-12-20 | 2027-12-21 | 2027-12-22 | 2027-12-23 | 2027-12-24 | 2027-12-27 | 2027-12-28 | 2027-12-29 | 2027-12-30 | 2027-12-31
Brown, Ben | 1_RS | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | Xcel PSCo Fall | Xcel PSCo Fall | Xcel PSCo Fall | Xcel PSCo Fall | Xcel PSCo Fall | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | Unavailable | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | Xcel PSCo Fall | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | Xcel PSCo Fall | Xcel PSCo Fall | Unavailable | Unavailable | Unavailable | Xcel PSCo Fall | Xcel PSCo Fall | Xcel PSCo Fall | Eversource 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | FPL Winter 2026 | FPL Winter 2026 | Unavailable | FPL Winter 2026 | Training | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Xcel PSCo & SPS | Transgrid 2026 | Transgrid 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | Unavailable | OPPD 2026 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | Unavailable | SHET RIIO-T3 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Unavailable | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | [12 empty] | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Unavailable | [83 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Glen-Findlay, Annie | 1_RS | Eversource 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | Unavailable | Minnkota PC 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Xcel PSCo Fall | Xcel PSCo Fall | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | NGUK 2025 | LGE Fall (Eng) | LGE Fall (Eng) | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Unavailable | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Unavailable | Unavailable | NV Energy 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Unavailable | Xcel NSP Fall 2025 | NV Energy 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Training | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Xcel HB 2026 | Xcel HB 2026 | Training | Training | Training | Training | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Unavailable | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Transgrid 2026 | Transgrid 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Administrative | SHET RIIO-T3 | SHET RIIO-T3 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Unavailable | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | Unavailable | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | NYPA Group A 2026 | NYPA Group A 2026 | UAT | HONI 2026 | HONI 2026 | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | Unavailable | [83 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Kucharczyk, Wojciech | 1_RS | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | Unavailable | Unavailable | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Avangrid CMP Engr | Avangrid CMP Engr | Training | Training | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | Lansing BWL LiDAR | Unavailable | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | Avangrid CMP Engr | Unavailable | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Training | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | Unavailable | Unavailable | LGE Fall (Eng) | FPL 2025 | FPL 2025 | Lansing BWL LiDAR | Lansing BWL LiDAR | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | SHET RIIO-T3 | Sunflower Electric | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | NGUS 2026 | NGUS 2026 | HONI 2026 | HONI 2026 | HONI 2026 | Unavailable | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | [61 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Lau, Zara | 1_RS | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | NGUS ACR | NGUS Fall TLE | HONI Patrol 2025 | NGUS Fall TLE | NGUS ACR | NGUS ACR | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo APC 2025 | SoCo APC 2025 | Xcel PSCo Fall | Xcel PSCo Fall | Xcel PSCo Fall | NGUS ACR | SSE SHET | SSE SHET | SSE SHET | SSE SHET | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | NGUS ACR | NGUS Fall TLE | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | NGUS ACR | SSE SHET | Xcel NSP Fall 2025 | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | NV Energy 2025 | SSE SHET | UAT | UAT | UAT | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | Training | Training | Training | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Training | Training | Training | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | FLOW | FLOW | FLOW | FLOW | Unavailable | Transgrid 2026 | Transgrid 2026 | FLOW | Transgrid 2026 | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | FLOW | Transgrid 2026 | OPPD 2026 | Transgrid 2026 | Transgrid 2026 | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | Unavailable | FLOW | FLOW | FLOW | FLOW | Unavailable | Unavailable | FLOW | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | FLOW | Sunflower Electric | Unavailable | Sunflower Electric | Sunflower Electric | FLOW | Sunflower Electric | SHET RIIO-T3 | Sunflower Electric | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | CMP Engr | CMP Engr | CMP Engr | CMP Engr | CMP Engr | CMP Engr | CMP Engr | CMP Engr | CMP Engr | CMP Engr | CMP Engr | CMP Engr | CMP Engr | CMP Engr | CMP Engr | [5 empty] | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | [72 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Mulero, Alberto | 1_RS | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | Unavailable | Unavailable | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | NGUS TLE | NGUS TLE | NGUS TLE | SoCo GPC 2025 | SoCo GPC 2025 | SoCo APC 2025 | SoCo APC 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUS TLE | NGUS TLE | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo APC 2025 | SoCo APC 2025 | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | NGUS Fall TLE | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | NGUS ACR | NGUS ACR | NGUS ACR | NGUS ACR | SoCo GPC Engr | NGUK 2025 | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | NGUK 2025 | NGUK 2025 | NGUK 2025 | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | Administrative | Administrative | Unavailable | Unavailable | Unavailable | NGUK 2025 | NGUK 2025 | Administrative | FPL Winter 2026 | FPL Winter 2026 | Administrative | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | HDR (NPPD) | Training | Administrative | Training | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | FPL Winter 2026 | Xcel HB 2026 | Xcel HB 2026 | ComEd Wood to Steel | ComEd Wood to Steel | ComEd Wood to Steel | ComEd Wood to Steel | ComEd Wood to Steel | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | ComEd Wood to Steel | ComEd Wood to Steel | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | OPPD 2026 | Unavailable | Xcel HB 2026 | Xcel PSCo & SPS | Xcel HB 2026 | Unavailable | Unavailable | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | OPPD 2026 | CHGE Spring 2026 | Xcel PSCo & SPS | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | Unavailable | CHGE Spring 2026 | CHGE Spring 2026 | HONI 500kV | HONI 500kV | HONI 500kV | HONI 500kV | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | CHGE Spring 2026 | Unavailable | CHGE Spring 2026 | CHGE Spring 2026 | HONI 500kV | HONI 500kV | OPPD 2026 | CHGE Spring 2026 | Sunflower Electric | Sunflower Electric | Administrative | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | [29 empty] | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | Unavailable | [83 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Murphy, Keiren | 1_RS | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | FPL 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | FPL 2025 | FPL 2025 | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | FPL 2025 | FPL 2025 | FPL 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | FPL 2025 | NGUS ACR | NGUS ACR | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Training | Training | NGUS ACR | Lansing BWL LiDAR | Lansing BWL LiDAR | Training | Training | FPL 2025 | FPL 2025 | Lansing BWL LiDAR | Training | Training | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | Training | Training | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | Training | Training | Training | Training | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | Administrative | Administrative | Training | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Administrative | Administrative | OPPD Spring 2025 | Administrative | NGUS S1 U2 Mapping | Training | Administrative | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | UAT | UAT | Unavailable | Unavailable | Administrative | UAT | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Training | Administrative | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | Lansing BWL LiDAR | Lansing BWL LiDAR | Administrative | NV Energy 2025 | NV Energy 2025 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Administrative | Transgrid 2026 | Transgrid 2026 | Administrative | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Administrative | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Administrative | Unavailable | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | HONI 2026 | Unavailable | Administrative | Administrative | HONI 2026 | HONI 2026 | HONI 2026 | Humelink Canopies | Humelink Canopies | SoCo GPC 2026 | Humelink Canopies | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | LGE Spring 2026 | LGE Spring 2026 | LGE Spring 2026 | LGE Spring 2026 | LGE Spring 2026 | LGE Spring 2026 | LGE Spring 2026 | LGE Spring 2026 | LGE Spring 2026 | LGE Spring 2026 | Unavailable | [83 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Phillpotts, Gregory | 1_RS | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | Eversource 2025 | Eversource 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | Unavailable | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | Unavailable | Unavailable | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | Unavailable | SoCo APC 2025 | SoCo APC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | NGUK 2025 | LGE Fall (Eng) | Eversource 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Powerlink CopperString | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Powerlink CopperString | Administrative | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Powerlink CopperString | Powerlink CopperString | Powerlink CopperString | Training | Training | Powerlink CopperString | Powerlink CopperString | Powerlink CopperString | Powerlink CopperString | Powerlink CopperString | Powerlink CopperString | Powerlink CopperString | Powerlink CopperString | Powerlink CopperString | Training | Powerlink CopperString | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | ComEd Wood to Steel | ComEd Wood to Steel | ComEd Wood to Steel | ComEd Wood to Steel | ComEd Wood to Steel | ComEd Wood to Steel | Powerlink MacIntyre | Powerlink MacIntyre | Powerlink MacIntyre | Powerlink MacIntyre | ComEd Wood to Steel | ComEd Wood to Steel | ComEd Wood to Steel | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Powerlink MacIntyre | Xcel PSCo & SPS | Xcel PSCo & SPS | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Powerlink CopperString | Powerlink CopperString | OPPD 2026 | OPPD 2026 | OPPD 2026 | NYPA Group A 2026 | NYPA Group A 2026 | Powerlink CopperString | Powerlink CopperString | NYPA Group A 2026 | NYPA Group A 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Unavailable | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | UAT | UAT | UAT | UAT | NYPA Group A 2026 | Powerlink CopperString | NYPA Group A 2026 | Unavailable | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | UAT | UAT | UAT | UAT | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | Westwood Minnesota | NYPA Group A 2026 | SoCo GPC 2026 | SoCo GPC 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | LGE Spring 2026 | LGE Spring 2026 | LGE Spring 2026 | LGE Spring 2026 | LGE Spring 2026 | LGE Spring 2026 | LGE Spring 2026 | LGE Spring 2026 | LGE Spring 2026 | LGE Spring 2026 | Unavailable |  |  |  |  | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | [64 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Skarbek, Andrzej | 1_RS | NGUS TLE | Training | NGUS TLE | Training | NGUS TLE | Training | Training | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Training | HONI Patrol 2025 | Training | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | Unavailable | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | LGE Spring 2025 | LGE Spring 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | Training | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Transgrid 2026 | Humelink Canopies | Humelink Canopies | Humelink Canopies | Unavailable | Humelink Canopies | Humelink Canopies | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | Transgrid 2026 | SHET RIIO-T3 | Humelink Canopies | Humelink Canopies | Humelink Canopies | Unavailable | Humelink Canopies | Humelink Canopies | Humelink Canopies | Humelink Canopies | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Training | Humelink Canopies | Humelink Canopies | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | Unavailable | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | [39 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Bernadic, Jakub | 1_RS | [5 empty] | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | NYPA Group D | NYPA Group D | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | NYPA Group D | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | Unavailable | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | NYPA Group D | NYPA Group D | NYPA Group D | SoCo GPC 2025 | SoCo GPC 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo APC 2025 | SoCo APC 2025 | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | Unavailable | Unavailable | Unavailable | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Veg) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | NGUK 2025 | Lansing BWL LiDAR | Lansing BWL LiDAR | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Powerlink CopperString | Ameren UAV Processing | Powerlink CopperString | Powerlink CopperString | Lansing BWL LiDAR | Powerlink MacIntyre | Powerlink MacIntyre | Training | Training | Training | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Xcel HB 2026 | Unavailable | Xcel HB 2026 | Xcel HB 2026 | Transgrid 2026 | Transgrid 2026 | Ameren UAV Processing | Ameren UAV Processing | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | LS Power Collinsville | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Ameren UAV Processing | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Ameren UAV Processing | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | SHET RIIO-T3 | SHET RIIO-T3 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | Unavailable | CHGE Spring 2026 | FLOW | FLOW | FLOW | FLOW | SHET RIIO-T3 | FLOW | SHET RIIO-T3 | FLOW | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | Ameren UAV Processing | Ameren UAV Processing | Unavailable | UAT | UAT | UAT | UAT | UAT | UAT | UAT | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | UAT | UAT | Ameren UAV Processing | ComEd CSX | Sunflower Electric | SHET RIIO-T3 | Avangrid CMP Veg 2026 | UAT | UAT | UAT | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | Unavailable | Unavailable | Unavailable | Unavailable | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | Unavailable | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | [39 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Alvarez, Maria | 1_RS | [40 empty] | Unavailable | [79 empty] | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Training | Training | Training | Unavailable | Training | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Transgrid 2026 | Unavailable | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | OPPD 2026 | Unavailable | SHET RIIO-T3 | OPPD 2026 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | Avangrid CMP Engr | Avangrid CMP Engr | Unavailable | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | NYPA Group A 2026 | FLOW | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | SHET RIIO-T3 | Unavailable | SHET RIIO-T3 | NYPA Group A 2026 | NYPA Group A 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | SHET RIIO-T3 | SHET RIIO-T3 | Training | Unavailable | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | Unavailable | SoCo GPC 2026 | Westwood Minnesota | SoCo GPC 2026 | Training | Training | Training | SoCo GPC 2026 | SoCo GPC 2026 | WSP EDN2 | WSP EDN2 | WSP EDN2 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | Unavailable | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | [5 empty] | Unavailable | Unavailable | [72 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Allott, Mathew | 2_GIS | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Training | Training | Training | Training | Training | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Training | Training | Training | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Xcel NSP Fall 2025 | Minnkota PC 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Minnkota PC 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | SSE SHET | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Lansing BWL LiDAR | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Training | Training | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Humelink Canopies | Humelink Canopies | Unavailable | Humelink Canopies | Humelink Canopies | Humelink Canopies | SHET RIIO-T3 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | SHET RIIO-T3 | SHET RIIO-T3 | Humelink Canopies | Humelink Canopies | UAT | UAT | UAT | Unavailable | Humelink Canopies | Humelink Canopies | Humelink Canopies | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | Unavailable | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 |  |  |  |  | Unavailable | Unavailable |  |  |  | Unavailable
Ditcher, Steven | 2_GIS | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | Unavailable | Unavailable | Unavailable | HONI 2024 | HONI 2024 | HONI 2024 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Unavailable | Unavailable | Training | Training | Training | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Training | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | NGUS ACR | NGUS ACR | NGUS Fall TLE | NGUS Fall TLE | NGUS Fall TLE | NGUS Fall TLE | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | NGUK 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | Unavailable | Unavailable | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | FPL Winter 2026 | FPL Winter 2026 | Training | Training | Training | Training | FPL Winter 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Xcel HB 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | OPPD 2026 | OPPD 2026 | Unavailable | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | Unavailable | Unavailable | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | Unavailable | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | [14 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Balmforth, Chloe | 2_GIS | Training | Unavailable | Unavailable | Unavailable | Unavailable | [10 empty] | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | [10 empty] | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | [64 empty] | Unavailable | Unavailable | [19 empty] | Unavailable | [14 empty] | Unavailable | [69 empty] | Unavailable | [64 empty] | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | [14 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Dunhill, Rachel | 2_GIS | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Administrative | NGUK 2025 | NGUK 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | NGUK 2025 | NGUK 2025 | Administrative | Administrative | Administrative | Administrative | Unavailable | Administrative | Unavailable | QA Team | Administrative | Administrative | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | Unavailable | QA Team | QA Team | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | Unavailable | QA Team | QA Team | QA Team | QA Team | Unavailable | Unavailable | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | GPC Eng | GPC Eng | GPC Eng | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | Unavailable | QA Team | QA Team | QA Team | Unavailable | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | Unavailable | QA Team | QA Team | QA Team | QA Team | QA Team | Unavailable | QA Team | QA Team | QA Team | QA Team | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Administrative | Administrative | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | Administrative | Administrative | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | Unavailable | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | Unavailable | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | [9 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Dyer, Rohan | 2_GIS | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Unavailable | Training | Training | Training | Training | Training | Training | Training | Training | Training | Unavailable | Training | Training | Training | Training | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | Unavailable | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | Unavailable | Unavailable | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | Unavailable | Unavailable | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | Unavailable | Training | Training | Training | Training | Unavailable | Training | Training | Training | Training | Unavailable | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | Unavailable | Unavailable | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | Unavailable | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | Unavailable | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | Unavailable | Unavailable | Unavailable | Unavailable | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | Unavailable | Unavailable | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | Unavailable | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | [14 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Limmer, David | 2_GIS | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Training | Training | Training | Training | Training | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | NGUS ACR | NGUS ACR | NGUS Fall TLE | NGUS Fall TLE | NGUS Fall TLE | NGUS Fall TLE | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | Unavailable | Unavailable | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Xcel HB 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | SHET RIIO-T3 | Unavailable | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | OPPD 2026 | OPPD 2026 | OPPD 2026 | Unavailable | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Unavailable | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | NYPA Group A 2026 | NYPA Group A 2026 | Unavailable | Unavailable | Unavailable | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | Unavailable | Unavailable | Unavailable | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | Unavailable | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | [14 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Handley-Watson, James | 2_GIS | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | Unavailable | Unavailable | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | SoCo GPC 2025 | Lansing BWL LiDAR | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | Training | Training | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Training | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Training | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Lansing BWL LiDAR | Training | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Lansing BWL LiDAR | Training | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Unavailable | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Unavailable | Unavailable | SSE SHET | SSE SHET | Unavailable | Unavailable | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Ameren UAV Processing | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | FPL Winter 2026 | Unavailable | FPL Winter 2026 | FPL Winter 2026 | Transgrid 2026 | Transgrid 2026 | FPL Winter 2026 | FPL Winter 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | FLOW | FLOW | FLOW | FLOW | Unavailable | FLOW | FLOW | Unavailable | Unavailable | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | Unavailable | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | Unavailable | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 |  |  |  |  | Unavailable | Unavailable |  |  |  | Unavailable
Keelty, Victoria | 2_GIS | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | Unavailable | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | Training | Training | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | NGUK 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | Administrative | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Training | Training | Training | Administrative | Training | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Training | Training | Training | Training | Training | Training | Training | Training | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL 2025 | SSE SHET | SSE SHET | Xcel HB 2026 | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Unavailable | Unavailable | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Unavailable | UAT | UAT | UAT | UAT | UAT | UAT | UAT | UAT | UAT | UAT | UAT | UAT | UAT | UAT | UAT | UAT | UAT | UAT | UAT | FLOW | FLOW | FLOW | FLOW | FLOW | Unavailable | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | Unavailable | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 |  |  |  |  | Unavailable | Unavailable |  |  |  | Unavailable
Keter, Titus | 2_GIS | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Unavailable | Unavailable | Unavailable | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | [64 empty] | Unavailable | Unavailable | [19 empty] | Unavailable | [14 empty] | Unavailable | [69 empty] | Unavailable | [83 empty] | Unavailable | Unavailable |  |  |  | Unavailable
King, Katie | 2_GIS | Unavailable | Xcel SPS HB Texas | Xcel SPS HB Texas | Xcel SPS HB Texas | Unavailable | Xcel SPS HB Texas | Xcel SPS HB Texas | Xcel SPS HB Texas | Xcel SPS HB Texas | Xcel SPS HB Texas | Training | Training | Training | Training | Unavailable | Unavailable | Xcel 5301 | Xcel 5301 | Xcel 5301 | Xcel 5301 | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | Xcel PSCo Fall | Xcel PSCo Fall | Xcel PSCo Fall | Xcel PSCo Fall | Xcel PSCo Fall | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | Unavailable | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | Unavailable | Unavailable | Unavailable | Unavailable | QA Team | QA Team | QA Team | QA Team | Ameren UAV Processing | Ameren UAV Processing | QA Team | QA Team | QA Team | QA Team | Ameren UAV Processing | Ameren UAV Processing | UAT | UAT | UAT | UAT | Transgrid 2026 | Unavailable | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | FLOW | FLOW | FLOW | FLOW | FLOW | Unavailable | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | FLOW | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | Unavailable | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | Unavailable | Unavailable | Unavailable | Unavailable | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | [9 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Lander, Lauren | 2_GIS | Unavailable | Unavailable | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | Eversource 2025 | Eversource 2025 | NYPA Group D | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | Unavailable | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | Unavailable | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | Unavailable | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | NGUS TLE | NGUS TLE | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | FPL 2025 | LGE Fall (Eng) | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Ameren UAV Processing | Ameren UAV Processing | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL 2025 | Training | Training | Training | Training | FPL Winter 2026 | FPL Winter 2026 | Transgrid 2026 | Transgrid 2026 | FPL Winter 2026 | Ameren UAV Processing | Ameren UAV Processing | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Ameren UAV Processing | Ameren UAV Processing | Ameren UAV Processing | Unavailable | QA Team | QA Team | QA Team | QA Team | Ameren UAV Processing | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | Unavailable | Unavailable | Unavailable | QA Team | Unavailable | Unavailable | Unavailable | Unavailable | QA Team | QA Team | QA Team | QA Team | QA Team | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | Unavailable | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | Unavailable | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | [19 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Mapley, Neil | 2_GIS | HONI Patrol 2025 | HONI Patrol 2025 | Holyoke | Holyoke | Holyoke | Holyoke | Holyoke | HONI 2024 | HONI 2024 | HONI 2024 | NYPA Group D | HONI 2024 | HONI Patrol 2025 | HONI 2024 | HONI 2025 PLS | HONI Patrol 2025 | NYPA Group D | NYPA Group D | NYPA Group D | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI Patrol 2025 | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI Patrol 2025 | HONI 115 kV Reporting | HONI 115 kV Reporting | SoCo APC 2025 | SoCo APC 2025 | Unavailable | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Lansing BWL LiDAR | Lansing BWL LiDAR | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | NGUS Fall TLE | FPL 2025 | Lansing BWL LiDAR | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Lansing BWL LiDAR | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | FPL 2025 | FPL 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | UAT | UAT | Training | Training | UAT | Training | Training | UAT | UAT | UAT | Training | Training | UAT | UAT | UAT | Lansing BWL LiDAR | Training | UAT | UAT | UAT | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Administrative | UAT | UAT | Transgrid 2026 | Unavailable | UAT | UAT | UAT | UAT | UAT | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Administrative | Administrative | Administrative | Administrative | Administrative | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Administrative | UAT | UAT | NYPA Group A 2026 | NYPA Group A 2026 | UAT | NYPA Group A 2026 | NYPA Group A 2026 | Unavailable | NYPA Group A 2026 | UAT | Avangrid CMP Veg 2026 | Unavailable | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | Unavailable | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 |  |  |  |  | Unavailable | Unavailable |  |  |  | Unavailable
Mckay, Matthew | 2_GIS | Xcel SPS HB Texas | Xcel SPS HB Texas | Xcel SPS HB Texas | Xcel SPS HB Texas | Xcel SPS HB Texas | Xcel SPS HB Texas | Xcel SPS HB Texas | Xcel SPS HB Texas | Xcel SPS HB Texas | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Eversource 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | Unavailable | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | Unavailable | Unavailable | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | Xcel PSCo Fall | Xcel PSCo Fall | Xcel PSCo Fall | Xcel PSCo Fall | Xcel PSCo Fall | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | Unavailable | Unavailable | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Powerlink CopperString | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | Xcel W3419 | QA Team | QA Team | QA Team | QA Team | QA Team | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | Unavailable | Unavailable | QA Team | QA Team | QA Team | QA Team | HONI DKPL2 | HONI DKPL2 | QA Team | QA Team | QA Team | GPC Eng | HONI DKPL2 | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | Unavailable | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | Unavailable | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | SoCo APC 2026 | SoCo APC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | Unavailable | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | [14 empty] | Unavailable | Unavailable |  |  |  | Unavailable
O'Connell, Luke | 2_GIS | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Unavailable | Training | Training | Training | Training | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | Unavailable | SoCo GPC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Training | HONI Patrol 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | Training | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | NGUS ACR | NGUS ACR | NGUS Fall TLE | NGUS Fall TLE | NGUS Fall TLE | NGUS Fall TLE | NGUK 2025 | NGUK 2025 | NGUK 2025 | Unavailable | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | NGUK 2025 | NGUK 2025 | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | Unavailable | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | Unavailable | Training | Training | Training | Training | Unavailable | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | FPL Winter 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | QA Team | QA Team | QA Team | Unavailable | QA Team | QA Team | QA Team | Unavailable | Unavailable | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | Unavailable | Unavailable | Unavailable | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | Unavailable | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | [14 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Pena, Bethania | 2_GIS | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | Unavailable | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | Training | Training | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | SSE SHET | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL 2025 | Training | Training | Unavailable | Unavailable | SSE SHET | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Xcel HB 2026 | Ameren UAV Processing | Ameren UAV Processing | Xcel HB 2026 | Xcel HB 2026 | Ameren UAV Processing | Ameren UAV Processing | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Unavailable | Unavailable | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Powerlink MacIntyre | Powerlink MacIntyre | Powerlink MacIntyre | Ameren UAV Processing | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Unavailable | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | QA Team | Humelink Canopies | Humelink Canopies | Humelink Canopies | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | Unavailable | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | [9 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Postgate, Emilie | 2_GIS | HONI 2024 | Holyoke | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | OPPD Spring 2025 | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | Unavailable | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | Unavailable | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | NGUS TLE | Unavailable | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | Eversource 2025 | Eversource 2025 | Eversource 2025 | NGUS Fall TLE | NGUS Fall TLE | NGUS ACR | NGUS ACR | NGUS Fall TLE | NGUS Fall TLE | NGUS Fall TLE | NGUS ACR | NGUS ACR | NGUS Fall TLE | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | LGE Fall (Eng) | FPL 2025 | FPL 2025 | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Unavailable | Unavailable | SSE SHET | SSE SHET | SSE SHET | Powerlink CopperString | Powerlink CopperString | Powerlink CopperString | Powerlink CopperString | Powerlink CopperString | Powerlink CopperString | FPL Winter 2026 | Training | Training | Training | Training | Training | Transgrid 2026 | Transgrid 2026 | FPL Winter 2026 | Transgrid 2026 | FPL Winter 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Transgrid 2026 | Powerlink MacIntyre | Powerlink MacIntyre | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | HONI 500kV | HONI 500kV | HONI 500kV | Unavailable | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | OPPD 2026 | OPPD 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | Unavailable | Unavailable | Unavailable | Unavailable | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | SoCo APC 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | [14 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Rawling, Alice | 2_GIS | Xcel SPS HB Texas | Xcel SPS HB Texas | Xcel SPS HB Texas | Xcel SPS HB Texas | Xcel SPS HB Texas | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | Unavailable | Unavailable | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | Xcel PSCo Fall | Xcel PSCo Fall | Xcel PSCo Fall | Xcel PSCo Fall | Xcel PSCo Fall | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Ameren Drone | Ameren Drone | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | SoCo GPC Engr | Xcel NSP Fall 2025 | SoCo GPC | SoCo GPC | Unavailable | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Administrative | Administrative | UAT | UAT | UAT | Unavailable | Administrative | UAT | UAT | UAT | Administrative | Administrative | UAT | UAT | UAT | UAT | UAT | Administrative | Administrative | Unavailable | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Unavailable | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Unavailable | Unavailable | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Unavailable | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Unavailable | Unavailable | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | UAT | UAT | UAT | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Transgrid 2026 | Administrative | Administrative | Unavailable | Unavailable | Administrative | Administrative | Administrative | Administrative | Administrative | Administrative | Administrative | Administrative | Unavailable | Administrative | Administrative | Administrative | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable |  |  |  | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable
Skrzypczynski, Filip | 2_GIS | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | Unavailable | Unavailable | Unavailable | NYPA Group D | NYPA Group D | NYPA Group D | Unavailable | Unavailable | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SCE Spring 2025 | Unavailable | Unavailable | SCE Spring 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo APC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | Unavailable | Unavailable | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | NGUS TLE | NGUS TLE | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Avangrid CMP Engr | Avangrid CMP Engr | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Unavailable | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | HDR (NPPD) | HDR (NPPD) | FPL Winter 2026 | FPL Winter 2026 | Training | Training | NV Energy 2025 | Unavailable | Unavailable | Transgrid 2026 | Unavailable | Unavailable | Unavailable | Unavailable | FPL Winter 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Xcel HB 2026 | ComEd Wood to Steel | ComEd Wood to Steel | ComEd Wood to Steel | ComEd Wood to Steel | ComEd Wood to Steel | ComEd Wood to Steel | ComEd Wood to Steel | ComEd Wood to Steel | Unavailable | Unavailable | ComEd Wood to Steel | ComEd Wood to Steel | ComEd Wood to Steel | Unavailable | Unavailable | ComEd Wood to Steel | Powerlink MacIntyre | Powerlink MacIntyre | Xcel PSCo & SPS | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Powerlink MacIntyre | Powerlink MacIntyre | Powerlink MacIntyre | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Powerlink MacIntyre | Powerlink MacIntyre | FPL Winter 2026 | Unavailable | FPL Winter 2026 | FPL Winter 2026 | SHET RIIO-T3 | SHET RIIO-T3 | FPL Winter 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | Unavailable | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | Unavailable | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | [14 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Webster, Joanne | 2_GIS | [40 empty] | Unavailable | [33 empty] | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE |  |  | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | [6 empty] | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Xcel NSP Fall 2025 | Unavailable | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | NGUK 2025 | Avangrid CMP Engr | Avangrid CMP Engr | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Ameren UAV Processing | FPL Winter 2026 | FPL Winter 2026 | Unavailable | Unavailable | Training | Training | Training | SSE SHET | SSE SHET | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Unavailable | Unavailable | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Unavailable | Unavailable | Unavailable | Transgrid 2026 | LS Power Collinsville | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | HONI DKPL2 | HONI DKPL2 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | Unavailable | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | Unavailable | Unavailable | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | Unavailable | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | Eversource 2026 | [9 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Schuler, Felix | 3_PLS | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI 2024 | HONI 2024 | HONI Patrol 2025 | HONI Patrol 2026 | HONI Patrol 2027 | NYPA Group D | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Unavailable | Training | Training | Training | Training | Unavailable | Training | Training | Training | Training | Training | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Unavailable | Unavailable | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Unavailable | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | FPL Winter 2026 | Unavailable | Unavailable | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | Unavailable | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | Unavailable | Unavailable | Unavailable | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | Unavailable | HONI Max Op | HONI Max Op | HONI Max Op | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | Unavailable | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | [25 empty] | Unavailable | [15 empty] | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | [9 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Bell, Darren | 3_PLS | HONI 2024 | Holyoke | Holyoke | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI 2025 PLS | Unavailable | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | FPL 2025 | FPL 2025 | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | FPL 2025 | FPL 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | FPL 2025 | OPPD Spring 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | Unavailable | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | UAT | UAT | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Transgrid 2026 | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | ComEd Wood to Steel | ComEd Wood to Steel | Transgrid 2026 | ComEd Wood to Steel | ComEd Wood to Steel | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | ComEd Wood to Steel | ComEd Wood to Steel | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | GPC Eng | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Transgrid 2026 | Administrative | HONI Max Op | CHGE Spring 2026 | CHGE Spring 2026 | Unavailable | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | Unavailable | Unavailable | Unavailable | CHGE Spring 2026 | CHGE Spring 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | [5 empty] | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | Unavailable | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | [6 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Birkin, Chris | 3_PLS | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | NYPA Group D | NYPA Group D | NYPA Group D | Eversource 2025 | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | Unavailable | NYPA Group D |  |  | NGUS TLE | NGUS TLE | NGUS TLE | NYPA Group D | NYPA Group D | NYPA Group D | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | NYPA Group D | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | NGUS Fall TLE | NGUS Fall TLE | Minnkota PC 2025 | LGE Spring 2025 | LGE Spring 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | Lansing BWL LiDAR | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Xcel HB 2026 | Unavailable | Unavailable | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Xcel PSCo & SPS | Powerlink MacIntyre | Powerlink MacIntyre | Powerlink MacIntyre | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | Unavailable | HONI Max Op | HONI Max Op | HONI Max Op | Unavailable | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | Unavailable | HONI Max Op | HONI Max Op | HONI Max Op | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | [22 empty] | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | [19 empty] | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | Unavailable | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | [6 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Hope, Matthew | 3_PLS | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | Unavailable | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | OPPD Spring 2025 | NGUS TLE | NGUS TLE | NGUS TLE | Unavailable | NGUS TLE | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | Unavailable | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | Unavailable | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | NGUS TLE | HONI Patrol 2025 | HONI Patrol 2026 | HONI Patrol 2027 | HONI Patrol 2028 | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI Patrol 2025 | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | Training | Training | Training | Training | NGUS TLE | Training | Training | Training | Training | NGUS TLE | NGUS TLE | NGUS TLE | Training | Training | Unavailable | Unavailable | NGUS TLE | NGUS TLE | Training | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Training | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Unavailable | Training | Training | Minnkota PC 2025 | Minnkota PC 2025 | LGE Spring 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | LS Power Collinsville | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | Training | Avangrid CMP Veg 2026 | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | Unavailable | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | Unavailable | Unavailable | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI 2026 | HONI 2026 | HONI 2026 | Unavailable | HONI 2026 | HONI 500kV | HONI 500kV | CHGE Spring 2026 | CHGE Spring 2026 | HONI 500kV | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | Unavailable |  |  |  | Unavailable | Unavailable | Unavailable | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | Unavailable | Unavailable | Unavailable | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | Unavailable | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | Unavailable | Unavailable | PG&E M4 | PG&E M4 | PG&E M4 | Unavailable
Hunter, Alex | 3_PLS | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | NGUS TLE | Unavailable | NGUS TLE | NGUS TLE | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | NGUS TLE | Unavailable | Unavailable | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | Unavailable | FPL 2025 | FPL 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | Unavailable | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | NV Energy 2025 | NV Energy 2025 | FPL 2025 | FPL 2025 | NV Energy 2025 | NV Energy 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | Unavailable | FPL 2025 | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | Unavailable | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | FPL Winter 2026 | FPL Winter 2026 | Administrative | FPL Winter 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | Unavailable | Unavailable | Unavailable | Unavailable | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | [9 empty] | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | Unavailable | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | [14 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Kidd, Lewis | 3_PLS | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NGUS TLE | NGUS TLE | Unavailable | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | Unavailable | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Unavailable | Unavailable | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | OPPD Spring 2025 | OPPD Spring 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | Unavailable | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | ComEd Wood to Steel | ComEd Wood to Steel | Transgrid 2026 | ComEd Wood to Steel | ComEd Wood to Steel | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | ComEd Wood to Steel | ComEd Wood to Steel | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | CHGE Spring 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Transgrid 2026 | Transgrid 2026 | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | Unavailable | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | Unavailable | Unavailable | Unavailable | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | Unavailable | Unavailable | PG&E M4 | PG&E M4 | PG&E M4 | Unavailable
Obora, Gregory | 3_PLS | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | Unavailable | HONI 2024 | HONI 2024 | Unavailable | Unavailable | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | Unavailable | HONI 2024 | HONI 2024 | HONI 2024 | Unavailable | Unavailable | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | Unavailable | Unavailable | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | NGUS TLE | NYPA Group D | NYPA Group D | NYPA Group D | Unavailable | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | FPL 2025 | NV Energy 2025 | FPL 2025 | FPL 2025 | FPL 2025 | Unavailable | NGUS Fall TLE | NGUS Fall TLE | FPL 2025 | FPL 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | NV Energy 2025 | NV Energy 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | Unavailable | Unavailable | Unavailable | Unavailable | HONI Max Op | HONI Max Op | Avangrid CMP Engr | Avangrid CMP Engr | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Training | Unavailable | Unavailable | Unavailable | FPL 2025 | Training | FPL Winter 2026 | FPL Winter 2026 | Unavailable | Unavailable | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | CHGE Spring 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | Unavailable | Unavailable | Unavailable | Unavailable | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | Unavailable | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | Unavailable | Unavailable | PG&E M4 | PG&E M4 | PG&E M4 | Unavailable
Pointon, James | 3_PLS | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | HONI 2024 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | HONI 2024 | OPPD Spring 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | Unavailable | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI Patrol 2025 | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | NGUS TLE | NGUS TLE | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Unavailable | Unavailable | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Unavailable | Unavailable | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Fall (Eng) | LGE Fall (Eng) | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Minnkota PC 2025 | Minnkota PC 2025 | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Unavailable | Unavailable | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Transgrid 2026 | Training | HONI Max Op | Unavailable | Unavailable | Unavailable | HONI Max Op | HONI Max Op | HONI Max Op | Unavailable | Unavailable | Unavailable | HONI Max Op | HONI Max Op | HONI Max Op | Unavailable | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | Unavailable | HONI Max Op | HONI Max Op | HONI Max Op | Unavailable | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | Unavailable | [5 empty] | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | Avangrid CMP Veg 2026 | [5 empty] | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | Unavailable | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | PG&E M4 | Unavailable | Unavailable | PG&E M4 | PG&E M4 | PG&E M4 | Unavailable
Smythe, Gee | 3_PLS | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | NYPA Group D | NYPA Group D | Unavailable | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | Unavailable | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | NGUS TLE | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | Unavailable | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | LGE Spring 2025 | LGE Spring 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Spring 2025 | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | NV Energy 2025 | LGE Fall (Eng) | LGE Fall (Eng) | LGE Fall (Eng) | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | Lansing BWL LiDAR | SSE SHET | Unavailable | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | SSE SHET | HONI Max Op | HONI Max Op | Training | Training | Training | Training | Training | Training | FPL Winter 2026 | FPL Winter 2026 | Unavailable | Unavailable | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | FPL Winter 2026 | FPL Winter 2026 | HONI Max Op | HONI 500kV | HONI 2026 | HONI 2026 | HONI 2026 | CHGE Spring 2026 | CHGE Spring 2026 | NYPA Group A 2026 | HONI 500kV | CHGE Spring 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | [18 empty] | Unavailable | Unavailable |  |  | Unavailable | Unavailable | Unavailable | Unavailable | [14 empty] | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | [13 empty] | Unavailable | Unavailable | Unavailable |  |  |  | Unavailable
Waterson, Kieron | 3_PLS | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | Unavailable | NYPA Group D | NYPA Group D | NYPA Group D | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | Unavailable | Unavailable | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI Patrol 2023 - Rework | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | Unavailable | Unavailable | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | OPPD Spring 2025 | HONI Patrol 2023 - Rework | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | Unavailable | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | Unavailable | Unavailable | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | Unavailable | Unavailable | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | Minnkota PC 2025 | NGUS Fall TLE | Minnkota PC 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | LGE Fall (Eng) | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | HONI Max Op | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | HONI Max Op | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | Avangrid CMP Engr | HONI Max Op | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | Unavailable | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | HONI Max Op | HONI Max Op | HONI Max Op | Unavailable | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | [6 empty] | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | Unavailable | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | HONI 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | [14 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Woznica, Tomasz | 3_PLS | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Eversource 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Eversource 2025 | Eversource 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Training | Unavailable | Unavailable | Training | Training | Training | Training | Training | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | Unavailable | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | HONI Max Op | HONI Max Op | HONI Max Op | HONI Max Op | Unavailable | Unavailable | HONI Max Op | HONI Max Op | HONI Max Op | Unavailable | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | [28 empty] | Unavailable | [15 empty] | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | [6 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Wolage, Robert | 3_PLS | Avangrid CMP Veg | Avangrid CMP Veg | Avangrid CMP Veg | Avangrid CMP Veg | HONI 2024 | Unavailable | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | Unavailable | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | Avangrid CMP Veg | HONI 2024 | HONI 2024 | HONI 2024 | Eversource 2025 | NYPA Group D | HONI 2024 | HONI 2024 | HONI 2024 | Unavailable | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | HONI 2024 | NYPA Group D | NYPA Group D | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | NYPA Group D | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | Unavailable | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | Unavailable | Unavailable | Unavailable | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | Unavailable | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | Minnkota PC 2025 | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | NYPA Group D | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | FPL 2025 | Minnkota PC 2025 | Unavailable | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | FPL 2025 | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | FPL 2025 | FPL 2025 | SSE SHET | SSE SHET | SSE SHET | Unavailable | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Unavailable | SSE SHET | SSE SHET | SSE SHET | SSE SHET | Unavailable | SSE SHET | NV Energy 2025 | NV Energy 2025 | NV Energy 2025 | UAT | NV Energy 2025 | SSE SHET | NV Energy 2025 | SSE SHET | SSE SHET | SSE SHET | SSE SHET | FPL 2025 | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | SSE SHET | NV Energy 2025 | NV Energy 2025 | Administrative | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | Unavailable | Unavailable | Unavailable | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | Unavailable | Unavailable | FPL Winter 2026 | FPL Winter 2026 | Unavailable | Unavailable | Unavailable | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | Unavailable | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | FPL Winter 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | OPPD 2026 | Unavailable | Unavailable | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | NYPA Group A 2026 | [20 empty] | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | Unavailable | Unavailable | Unavailable | Unavailable | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 | FPL Summer 2026 |  |  |  | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | NGUS 2026 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | SHET RIIO-T3 | [6 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Mumford, Mark | 2_GIS | [30 empty] | ComEd L0709/L0710 | [9 empty] | Unavailable | [9 empty] | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | HONI 115 kV Reporting | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | NGUS TLE | [15 empty] | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 | SoCo GPC 2025 |  |  | HONI DKPL | Xcel MNEC | Xcel MNEC | Xcel MNEC | Xcel MNEC |  | Xcel MNEC | Xcel MNEC | Xcel MNEC | Unavailable | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | [10 empty] | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable
Beznea, Mihai | 1_RS | [10 empty] | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | HONI 2025 PLS | [26 empty] | Unavailable | [49 empty] | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | Xcel MNEC | Xcel MNEC | SoCo GPC Engr | SoCo GPC Engr | SoCo GPC Engr | [28 empty] | Unavailable | Unavailable |  |  |  | Unavailable
Birkin, Chris | 2_GIS | [40 empty] | Unavailable |  | NGUS TLE | NGUS TLE | [199 empty] | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | CHGE Spring 2026 | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric
Pointon, James | 2_GIS | [40 empty] | Unavailable | [207 empty] | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | [7 empty] | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric
Brown, Ben | 2_GIS | [40 empty] | Unavailable | [211 empty] | Humelink Canopies | Humelink Canopies | Humelink Canopies | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric | Sunflower Electric
Mulero, Alberto | 2_GIS | [40 empty] | Unavailable | [215 empty] | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | Xcel NSP Spring 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026 | SoCo GPC 2026
Skarbek, Andrzej | 2_GIS | [40 empty] | Unavailable
Skarbek, Andrzej | 2_GIS | [40 empty] | Unavailable
Shires, Charles | 3_PLS | [40 empty] | Unavailable | [64 empty] | NGUS TLE | NGUS TLE | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 | Minnkota PC 2025 |  |  | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable | Unavailable
Note on CT1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @luke.beaumont@nmgroup.com Im redoing capacity Assigned to luke.beaumont@nmgroup.com
Note on EM1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @luke.beaumont@nmgroup.com Xcel this and next week - those are my placeholders. feel free to change Reply: Placeholder are fine. NV energy Ortho QC might need to come into JAn if not ready for Annie Christmas days. That can push NGUK further down But any edits can wait for 2nd Jan.
Note on ER1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @seweryn.cieslik@nmgroup.com let me knwwo if should resource phase 2 here after your call with Ben Kostas Assigned to seweryn.cieslik@nmgroup.com
Note on GZ1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @seweryn.cieslik@nmgroup.com when im back will update PROD to reduce total TG Ortho hours by around 100. I will want to plan isn WSP and the other new projects eversoure/nypa. Do you think those details will bee in the planner when im back from AL? Assigned to seweryn.cieslik@nmgroup.com
Note on HE1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @luke.beaumont@nmgroup.com redue total TG Ortho hours ans stretch? Assigned to luke.beaumont@nmgroup.com
Note on HJ1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: FPL FLI here? looking at pls FPL starts much sooner? @luke.beaumont@nmgroup.com if TG can accomadde ortho less hours week earlier for this task? Assigned to luke.beaumont@nmgroup.com
Note on HP1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @luke.beaumont@nmgroup.com CMP veg and WSP here? or week sooner. Assigned to luke.beaumont@nmgroup.com
Note on II1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Stretch Xcel Lidar Build for veg scope to make room for HONI here
Note on IS1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add FLOW staff, reducve HONI. Add in SOCO r veg/products only
Note on JR1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FPL From here
Note on JS1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: LGE from here
Note on JW1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: LB - 3 weeks AL
Note on KB1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NGUS/Eversource from here
Note on KG1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CMP Engineering from here
Note on BF2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Start of APC oblique hours 618 out of 918 hours (300 mya be covered with OPS resources) Reply: These are noit exact start date (swappable with previous APC ortho QC input)
Note on BP2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @dominic.wilson@nmgroup.com NGUS??
Note on CW2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: oblique UAT
Note on CX2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: oblique. UAT
Note on FV2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @seweryn.cieslik@nmgroup.com this would overlap with Transgrid 2026 better to bring SHET forward away from that?
Note on HE2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @seweryn.cieslik@nmgroup.com when do we hear about SSE phase 2 or get approval to start BUILD? At this point think can reduce TG ortho (will review) and two people start SSE RS checks. This poiitn also epxecet JP and MH alread back with PLS Assigned to seweryn.cieslik@nmgroup.com Reply: assume it can be started when resources allow. no need to hear from Projects
Note on IN3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FLOW
Note on HE4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @luke.beaumont@nmgroup.com review closer to time start date Assigned to luke.beaumont@nmgroup.com
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GPC urgent report not a Production product - 2 weeks
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GPC urgent report not a Production product - 1 week
Note on GK5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @seweryn.cieslik@nmgroup.com for Project flow do you want a specific projecst code or ok as UAT? Assigned to seweryn.cieslik@nmgroup.com
Note on IN5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FLOW
Note on BK6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @carlos.fuentes@nmgroup.com @luke.beaumont@nmgroup.com @dominic.wilson@nmgroup.com NGUS??? Reply: Xcel + others indeed to fit in RS
Note on BF7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Start of GPC oblique hours 518 hours 7:40 AM Today These are noit exact start date (swappable with previous GPC ortho QC input)
Note on CV7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: rework + EO
Note on EJ7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @keiren.murphy@nmgroup.com NMIP25122 Assigned to keiren.murphy@nmgroup.com
Note on GZ8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: if not immediate need to work on OPPD/other project assign some time to review cont oblique and see what feedback on none staking tabel approach along with existing workflow he's benign doing on the side. Worked well for comed/lansing/xcel sop look to stanardise
Note on JN8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Blank to cover SOCO obliques
Note on JM10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @seweryn.cieslik@nmgroup.com after next week will review rapid veg numbers feel ive overestimated. Here Jakub will likely go to xcel or HONI Reply: but may keep numbers as they are as buffer in case issue with tool uat etc/ new deliverables. Then reduce when that is more ceratin
Note on IS11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SOCO GPC from here but also bit sooner
Note on FB15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com there is a QA Team task to chose from. please use it for Rachel and her team Assigned to dominic.wilson@nmgroup.com
Note on JC15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @dominic.wilson@nmgroup.com allocate QA team hours across HONI and SoCos Reply: all QA team or just a couple of them? Reply: all, please Reply: if some projects pop up, this can be adjusted closer to the date
Note on CP29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @dominic.wilson@nmgroup.com Eversource?
Note on DD29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com Assigned to dominic.wilson@nmgroup.com
Note on LK31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: START NGUS
Note on HF34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Rework - NMCP25032 HONI - E511V
Note on IO34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: QC
Note on KB35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FPL Summer - Captured 11-16 Jul
Note on KL35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FPL Summer - Capture 11-16 Jul
Note on H37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Apprenticeship
Note on K37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sick
Note on L37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sick
Note on KB37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FPL Summer - Captured 11-16 Jul
Note on KL37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FPL Summer - Capture 11-16 Jul
Note on EC38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @carlos.fuentes@nmgroup.com ? Assigned to carlos.fuentes@nmgroup.com Reply: James was waiting to build the TOIL to book that time, he send the request now
Note on HA38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @seweryn.cieslik@nmgroup.com NGUS Rework Assigned to seweryn.cieslik@nmgroup.com
Note on P41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Funeral to attend
Note on GL41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Schedule Training on FPL Modelling @seweryn.cieslik@nmgroup.com
Note on DI42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Allocated time for NYPA D Rework - IMS-371
Note on HK42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: compassionate leave
Note on HL42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: compassionate leave

## Teams Breakdown
Active | Project | Discipline | Planned HRS | HRS Assigned | HRS remaining | time axis 2025-06-30 to 2027-12-20
TRUE | Administrative | 1_RS |  | 155.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6 | 0 | 6.8 | 13.6 | 20.4 | 13.175 | 6.8 | 6.8 | 13.6 | 0 | 6.8 | 0 | 0 | 0 | 0 | 0 | 13.6 | 0 | 6.8 | 13.6 | 0 | 0 | 0 | 13.6 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | Ameren UAV Processing | 1_RS | 8 | 54.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 0 | 0 | 6.8 | 6.8 | 0 | 0 | 0 | 0 | 6.8 | 6.8 | 0 | 0 | 0 | 0 | 13.6 | 0 | 0 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | Avangrid CMP Engr | 1_RS | 60 | 61.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 27.2 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | Avangrid CMP Veg 2026 | 1_RS | 195 | 209.1 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.2 | 66.3 | 54.4 | 27.2 | 27.2 | 0 | 0 | 0 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | CHGE Spring 2026 | 1_RS | 90 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 13.6 | 68 | 20.4 | 0 | 6.8 | 13.6 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | CMP Eng 2026 | 1_RS | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | ComEd CSX | 1_RS | 20 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | Eversource 2026 | 1_RS | 170 | 170 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 68 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | FLOW | 1_RS |  | 1033.6 | 714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.2 | 6.8 | 6.8 | 13.6 | 34 | 34 | 47.6 | 34 | 6.8 | 6.8 | 0 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | FPL Summer 2026 | 1_RS | 145 | 170 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 102 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | FPL Winter 2026 | 1_RS | 240 | 265.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6 | 95.2 | 81.6 | 27.2 | 20.4 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | GPC Eng | 1_RS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | HONI 2026 | 1_RS | 420 | 374 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 40.8 | 20.4 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 34 | 34 | 34 | 34 | 20.4 | 27.2 | 0 | 34 | 34 | 20.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | HONI 500kV | 1_RS | 24 | 40.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6 | 13.6 | 0 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | HONI Darlington Nuclear | 1_RS | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | Humelink Canopies | 1_RS | 28 | 115.6 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.4 | 13.6 | 0 | 20.4 | 27.2 | 20.4 | 0 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | LGE Spring 2026 | 1_RS | 125 | 131.75 | 131.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.875 | 65.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | NGUS 2026 | 1_RS | 325 | 285.6 | 285.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 34 | 102 | 68 | 0 | 47.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | NYPA Group A 2026 | 1_RS | 215 | 378.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.125 | 6.375 | 45.9 | 121.125 | 39.95 | 52.7 | 53.975 | 39.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | OPPD 2026 | 1_RS | 105 | 192.525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4 | 0 | 6.8 | 53.125 | 68 | 6.8 | 0 | 20.4 | 27.2 | 0 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | Powerlink CopperString | 1_RS | 45 | 147.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.375 | 6.375 | 19.125 | 52.275 | 25.5 | 6.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.75 | 12.75 | 0 | 0 | 0 | 6.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | Powerlink MacIntyre | 1_RS | 40 | 45.475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6 | 0 | 0 | 0 | 25.5 | 0 | 0 | 6.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | SHET RIIO-T3 | 1_RS | 450 | 312.8 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.2 | 61.2 | 61.2 | 47.6 | 61.2 | 0 | 20.4 | 20.4 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | SoCo APC 2026 | 1_RS | 800 | 837.25 | 837.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88.4 | 88.4 | 88.4 | 54.4 | 79.475 | 40.8 | 40.8 | 27.2 | 59.925 | 59.925 | 59.925 | 40.8 | 27.2 | 27.2 | 27.2 | 27.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | SoCo GPC 2026 | 1_RS | 800 | 801.125 | 790.925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 3.4 | 19.55 | 47.6 | 68 | 68 | 39.1 | 45.475 | 45.475 | 45.475 | 13.6 | 34 | 27.2 | 27.2 | 39.95 | 39.95 | 39.95 | 27.2 | 40.8 | 40.8 | 40.8 | 40.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | Sunflower Electric | 1_RS | 270 | 122.4 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6 | 27.2 | 20.4 | 20.4 | 27.2 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | Training | 1_RS |  | 535.925 | 27.2 | 47.6 | 47.6 | 34 | 47.6 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6 | 13.6 | 13.6 | 13.6 | 13.6 | 13.6 | 13.6 | 6.8 | 0 | 0 | 6.8 | 13.6 | 6.8 | 33.15 | 0 | 81.175 | 47.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 0 | 27.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | Transgrid 2026 | 1_RS | 2750 | 2026.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.6 | 68 | 102 | 136 | 190.4 | 224.4 | 217.6 | 210.8 | 197.2 | 142.8 | 156.4 | 197.2 | 68 | 34 | 13.6 | 13.6 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | UAT | 1_RS |  | 180.2 | 20.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 13.6 | 0 | 0 | 0 | 0 | 13.6 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.75 | 12.75 | 27.2 | 52.7 | 13.6 | 20.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | Westwood Minnesota | 1_RS | 24 | 13.175 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.375 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | WSP EDN2 | 1_RS | 30 | 20.4 | 20.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | Xcel NSP Spring 2026 | 1_RS | 670 | 515.525 | 352.325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 27.2 | 68 | 34 | 46.325 | 65.875 | 65.875 | 99.875 | 74.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | Administrative | 2_GIS |  | 272 | 27.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 0 | 0 | 13.6 | 13.6 | 13.6 | 47.6 | 20.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 13.6 | 20.4 | 27.2 | 54.4 | 0 | 6.8 | 0 | 13.6 | 0 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | Ameren UAV Processing | 2_GIS | 36 | 128.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6 | 6.375 | 0 | 0 | 27.2 | 19.975 | 0 | 0 | 0 | 20.4 | 13.6 | 0 | 0 | 0 | 20.4 | 0 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | Avangrid CMP Engr | 2_GIS | 150 | 176.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.75 | 65.875 | 52.275 | 20.4 | 0 | 0 | 12.75 | 0 | 0 | 0 | 12.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | Avangrid CMP Veg 2026 | 2_GIS | 400 | 275.4 | 65.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.8 | 27.2 | 68 | 73.525 | 65.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | CHGE Spring 2026 | 2_GIS | 50 | 129.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.875 | 25.5 | 45.475 | 26.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | CMP Eng 2026 | 2_GIS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | ComEd CSX | 2_GIS | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | Eversource 2026 | 2_GIS | 850 | 852.55 | 852.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 99.875 | 133.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | FLOW | 2_GIS |  | 727.6 | 496.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59.5 | 39.95 | 65.875 | 65.875 | 34 | 34 | 27.2 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 27.2 | 34 | 34 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | FPL Summer 2026 | 2_GIS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | FPL Winter 2026 | 2_GIS | 420 | 313.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107.1 | 13.6 | 114.325 | 19.55 | 0 | 0 | 0 | 0 | 0 | 0 | 13.175 | 26.35 | 19.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | GPC Eng | 2_GIS |  | 27.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.4 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | HONI 2026 | 2_GIS | 5000 | 5043.475 | 5043.475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 27.2 | 95.2 | 102 | 102 | 235.875 | 188.7 | 235.875 | 269.875 | 229.075 | 269.875 | 303.875 | 303.875 | 284.75 | 371.875 | 403.75 | 396.95 | 383.35 | 403.75 | 133.875 | 133.875 | 133.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | HONI 500kV | 2_GIS | 30 | 20.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | HONI Darlington Nuclear | 2_GIS | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | HONI DKPL2 | 2_GIS | 8 | 33.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6 | 6.8 | 12.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | Humelink Canopies | 2_GIS | 60 | 108.8 | 40.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6 | 20.4 | 0 | 13.6 | 20.4 | 0 | 0 | 40.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | LGE Spring 2026 | 2_GIS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | NGUS 2026 | 2_GIS | 750 | 748 | 748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | NYPA Group A 2026 | 2_GIS | 1000 | 911.2 | 761.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.4 | 0 | 54.4 | 13.6 | 61.2 | 81.6 | 122.4 | 136 | 81.6 | 68 | 68 | 68 | 68 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | OPPD 2026 | 2_GIS | 100 | 217.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27.2 | 68 | 27.2 | 68 | 27.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | Powerlink CopperString | 2_GIS | 60 | 47.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 0 | 13.6 | 27.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | Powerlink MacIntyre | 2_GIS | 20 | 81.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 6.8 | 13.6 | 34 | 6.8 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | QA Team | 2_GIS |  | 2101.2 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 136 | 129.2 | 136 | 95.2 | 68 | 122.4 | 129.2 | 108.8 | 95.2 | 88.4 | 108.8 | 95.2 | 81.6 | 95.2 | 102 | 129.2 | 122.4 | 115.6 | 88.4 | 47.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | SHET RIIO-T3 | 2_GIS | 800 | 839.375 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 209.1 | 249.475 | 95.2 | 27.2 | 34 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | SoCo APC 2026 | 2_GIS | 1520 | 1560.175 | 1560.175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.4 | 0 | 34 | 47.6 | 34 | 68 | 0 | 102 | 170 | 136 | 129.2 | 170 | 108.8 | 133.875 | 133.875 | 86.275 | 86.275 | 99.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | SoCo GPC 2026 | 2_GIS | 1770 | 1764.6 | 1764.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.4 | 13.6 | 27.2 | 68 | 197.2 | 217.6 | 156.4 | 274.975 | 220.575 | 233.75 | 93.5 | 79.9 | 68 | 93.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | Sunflower Electric | 2_GIS | 900 | 787.525 | 719.525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 154.275 | 167.875 | 201.875 | 65.875 | 31.875 | 31.875 | 65.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | Training | 2_GIS |  | 2299.675 | 0 | 108.8 | 102 | 129.2 | 102 | 102 | 102 | 95.2 | 68 | 54.4 | 0 | 102 | 68 | 68 | 68 | 68 | 68 | 54.4 | 47.6 | 0 | 87.55 | 6.375 | 6.375 | 20.4 | 6.375 | 6.375 | 0 | 0 | 0 | 0 | 0 | 155.55 | 136 | 115.6 | 115.6 | 222.275 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | Transgrid 2026 | 2_GIS | 3500 | 2483.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 169.575 | 241.4 | 215.9 | 242.675 | 209.1 | 175.1 | 255.85 | 383.775 | 323.85 | 94.35 | 110.925 | 27.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | UAT | 2_GIS |  | 427.125 | 40.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.4 | 20.4 | 20.4 | 32.725 | 20.4 | 20.4 | 20.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6 | 20.4 | 61.2 | 0 | 0 | 20.4 | 27.2 | 47.6 | 40.8 | 40.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | Westwood Minnesota | 2_GIS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | WSP EDN2 | 2_GIS | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | Xcel NSP Spring 2026 | 2_GIS | 940 | 782.85 | 782.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161.075 | 256.275 | 201.875 | 65.875 | 65.875 | 31.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | Administrative | 3_PLS |  | 19.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 6.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | Avangrid CMP Engr | 3_PLS | 135 | 267.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38.25 | 31.875 | 31.875 | 51 | 95.625 | 19.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | Avangrid CMP Veg 2026 | 3_PLS | 89 | 135.575 | 115.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.375 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6 | 13.6 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | CHGE Spring 2026 | 3_PLS | 193 | 479.825 | 154.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 0 | 0 | 0 | 13.6 | 40.375 | 122.4 | 141.95 | 154.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | CMP Eng 2026 | 3_PLS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | ComEd CSX | 3_PLS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | Eversource 2026 | 3_PLS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | FPL Summer 2026 | 3_PLS | 975 | 956.25 | 956.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.875 | 57.375 | 38.25 | 63.75 | 63.75 | 63.75 | 63.75 | 63.75 | 63.75 | 63.75 | 63.75 | 63.75 | 63.75 | 63.75 | 63.75 | 63.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | FPL Winter 2026 | 3_PLS | 1029 | 1546.3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110.925 | 150.45 | 164.05 | 190.825 | 216.75 | 164.05 | 143.65 | 192.3125 | 136 | 77.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | GPC Eng | 3_PLS |  | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | HONI 2026 | 3_PLS | 878 | 887.825 | 787.525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 87.125 | 6.375 | 0 | 0 | 0 | 0 | 0 | 0 | 25.5 | 97.75 | 97.75 | 119 | 99.875 | 79.9 | 99.875 | 99.875 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | HONI 500kV | 3_PLS | 32 | 32.725 | 6.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 0 | 19.55 | 6.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | HONI Darlington Nuclear | 3_PLS | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | HONI Max Op | 3_PLS | 2025 | 1129.225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.125 | 6.375 | 0 | 79.9 | 174.675 | 53.55 | 0 | 0 | 25.925 | 73.525 | 132.6 | 113.9 | 154.275 | 181.475 | 107.525 | 6.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | LGE Spring 2026 | 3_PLS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | NGUS 2026 | 3_PLS | 2123 | 2119.9 | 2119.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101.15 | 201.875 | 201.875 | 201.875 | 201.875 | 201.875 | 201.875 | 201.875 | 201.875 | 201.875 | 201.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | NYPA Group A 2026 | 3_PLS | 1369 | 1370.2 | 1363.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 6.8 | 165.75 | 329.375 | 331.5 | 291.125 | 238.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | OPPD 2026 | 3_PLS | 367 | 418.625 | 208.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108.375 | 102 | 112.625 | 95.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | PG&E M4 | 3_PLS | 0 | 2908.7 | 2908.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.875 | 65.875 | 65.875 | 99.875 | 87.125 | 87.125 | 99.875 | 111.775 | 105.4 | 131.75 | 131.75 | 131.75 | 131.75 | 131.75 | 131.75 | 131.75 | 124.95 | 97.75 | 131.75 | 131.75 | 131.75 | 131.75 | 131.75 | 131.75 | 105.4 | 79.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | Powerlink MacIntyre | 3_PLS | N/A | 20.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | SHET RIIO-T3 | 3_PLS | 4313 | 268.6 | 248.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167.875 | 80.325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | SoCo APC 2026 | 3_PLS | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | SoCo GPC 2026 | 3_PLS | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | Sunflower Electric | 3_PLS | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | Training | 3_PLS |  | 985.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93.5 | 93.5 | 80.75 | 74.375 | 74.375 | 74.375 | 74.375 | 40.8 | 0 | 68 | 68 | 61.2 | 47.6 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 33.575 | 19.975 | 0 | 6.8 | 6.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | Transgrid 2026 | 3_PLS | 512 | 599.675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 0 | 0 | 47.6 | 68 | 86.7 | 79.9 | 79.9 | 81.175 | 47.6 | 68 | 27.2 | 0 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TRUE | UAT | 3_PLS |  | 19.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | Westwood Minnesota | 3_PLS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FALSE | WSP EDN2 | 3_PLS | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Luke Beaumont | 1_RS |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Dom Wilson | 2_GIS |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Carlos Fuentes | 3_PLS |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  | TOTAL |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Luke Beaumont | 1_RS | Total Availability |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Dom Wilson | 2_GIS | Total Availability |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| Carlos Fuentes | 3_PLS | Total Availability |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | Product | km/h | [20 empty] | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30
|  |  |  | Tiled Point Cloud | 5 | [20 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | Continuous Oblique Imagery | 12 | [20 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | Developed Oblique Imagery | 9 | [20 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | Classified Tiled Point Cloud | 5 | [20 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | 2D Topographic Vectors | 8 | [20 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | PLS CADD Model | 3 | [20 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
|  |  |  | Temperature Calculations | 10 | [20 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[63 empty] | 2nd RSer |  |  |  | 3rd?
Note on AU24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @luke.beaumont@nmgroup.com probably this will shift by some time as we might not get the 2nd part of project awarded right away. Bear this in mind and anticipate xcel obliques or fli coming your way at that point Assigned to luke.beaumont@nmgroup.com Reply: hi thanks will review full on monday. Likley Greg and Alberto will not move to TG last two weeks of march and they will bemused for Obliques etc which is not yet on my capacity. Those TG hours can move forwrada nd replace the SHET hours here
Note on AW29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I think there are 130 hrs left on ortho QC 1 total reaction Seweryn Cieslik reacted with 😎 at 2026-04-17 13:39 PM Reply: @luke.beaumont@nmgroup.com
Note on B35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com Assigned to dominic.wilson@nmgroup.com
Note on B41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com Assigned to dominic.wilson@nmgroup.com
Note on BM41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com RS support available - speak to Luke please. Numbers show one and then more ppl available. Good to start Eversource earlier Assigned to dominic.wilson@nmgroup.com
Note on B45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com I added GPC Eng - please allocate hours Assigned to dominic.wilson@nmgroup.com
Note on B52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com Assigned to dominic.wilson@nmgroup.com
Note on D58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com please allocate from mid may Assigned to dominic.wilson@nmgroup.com
Note on B77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @carlos.fuentes@nmgroup.com added GPC Eng - please allocate hours Assigned to carlos.fuentes@nmgroup.com
Note on F85: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @carlos.fuentes@nmgroup.com Are these hours (191 scheduled vs 340 planned hours) for FPL PLS work accurate? Assigned to carlos.fuentes@nmgroup.com
Note on AS102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @seweryn.cieslik@nmgroup.com dont think this number take into account FLOW. When put zara hours to a normal project goes down to 0 Assigned to seweryn.cieslik@nmgroup.com
Note on BK104: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com post NYPA PLS resources available. Speak to Carlos - allocate one or two for GIS tasks? Assigned to dominic.wilson@nmgroup.com
Note on X105: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com @luke.beaumont@nmgroup.com Assigned to dominic.wilson@nmgroup.com
Note on E106: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @ben.bottoms@nmgroup.com I have no concept to visualise this data. any ideas? Assigned to ben.bottoms@nmgroup.com Reply: Does the 1,383 km in cell AB93 mean if the RS team was 100% on build (and nothing else), they could produce a max 1,383 km per week? I'll think more about this. For RS (as an example), we need to somehow normalize the 3 product options into an average weekly (or monthly) amount and then convert that to a SPU number. I'm not sure how to do that. But if we have it down to a SPU "capacity" estimate for RS, GIS and PLS then we can have a graph like the one I was showing with the utilized hours. Monthly might be easier for SPUs as you can could probably make a solid guess at the SPU's we will deliver by month for Dec, Jan & Feb. We can chat more on Friday

## Capacity
Project code | Project name | % completed | HRS Assigned | Planned HRS | HRS remaining | % of effort spent | time axis 2025-06-30 to 2027-01-11
NMCP24017 | HONI 2024 | 100% | 0 | 4547.9 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMCP25032 | HONI Patrol 2025 | 100% | 0 | 347 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMCP25032_1 | HONI 2025 PLS | 100% | 0 | 526.77 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP25007 | NGUS TLE | 100% | 0 | 1668 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP25028 | Lansing BWL LiDAR | 100% | 0 | 289 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP25011 | Avangrid CMP Veg | 100% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP25012 | NYPA Group D | 100% | 0 | 730 | 0 | 0% | 2025-06-30: 0; 2025-07-07: 0; 2025-07-14: 0; 2025-07-21: 0; 2025-07-28: 0; 2025-08-04: 0; 2025-08-11: 0; 2025-08-18: 0; 2025-08-31: 0; 2025-09-01: 0; 2025-09-08: 0; 2025-09-15: 0; 2025-09-22: 0; 2025-09-29: 0; 2025-10-06: 0; 2025-10-13: 0; 2025-10-20: 0; 2025-10-27: 0; 2025-11-03: 0; 2025-11-10: 0; 2025-11-17: 0; 2025-11-24: 0; 2025-12-01: 0; 2025-12-08: 0; 2025-12-15: 0; 2025-12-22: 0; 2025-12-29: 0; 2026-01-05: 0; 2026-01-12: 0; 2026-01-19: 0; 2026-01-26: 0; 2026-02-02: 0; 2026-02-09: 0; 2026-02-16: 0; 2026-02-23: 0; 2026-03-02: 0; 2026-03-09: 0; 2026-03-16: 0; 2026-03-23: 0; 2026-03-30: 0
NMIP25015 | OPPD Spring 2025 | 100% | 0 | 306 | 0 | 0% | 2025-06-30: 0; 2025-07-07: 0; 2025-07-14: 0; 2025-07-21: 0; 2025-07-28: 0; 2025-08-04: 0; 2025-08-11: 0; 2025-08-18: 0; 2025-08-31: 0; 2025-09-01: 0; 2025-09-08: 0; 2025-09-15: 0; 2025-09-22: 0; 2025-09-29: 0; 2025-10-06: 0; 2025-10-13: 0; 2025-10-20: 0; 2025-10-27: 0; 2025-11-03: 0; 2025-11-10: 0; 2025-11-17: 0; 2025-11-24: 0; 2025-12-01: 0; 2025-12-08: 0; 2025-12-15: 0; 2025-12-22: 0; 2025-12-29: 0; 2026-01-05: 0; 2026-01-12: 0; 2026-01-19: 0; 2026-01-26: 0; 2026-02-02: 0; 2026-02-09: 0; 2026-02-16: 0; 2026-02-23: 0; 2026-03-02: 0; 2026-03-09: 0; 2026-03-16: 0; 2026-03-23: 0; 2026-03-30: 0
NMIP25017 | Holyoke | 100% | 0 | 80 | 0 | 0% | 2025-06-30: 0; 2025-07-07: 0; 2025-07-14: 0; 2025-07-21: 0; 2025-07-28: 0; 2025-08-04: 0; 2025-08-11: 0; 2025-08-18: 0; 2025-08-31: 0; 2025-09-01: 0; 2025-09-08: 0; 2025-09-15: 0; 2025-09-22: 0; 2025-09-29: 0; 2025-10-06: 0; 2025-10-13: 0; 2025-10-20: 0; 2025-10-27: 0; 2025-11-03: 0; 2025-11-10: 0; 2025-11-17: 0; 2025-11-24: 0; 2025-12-01: 0; 2025-12-08: 0; 2025-12-15: 0; 2025-12-22: 0; 2025-12-29: 0; 2026-01-05: 0; 2026-01-12: 0; 2026-01-19: 0; 2026-01-26: 0; 2026-02-02: 0; 2026-02-09: 0; 2026-02-16: 0; 2026-02-23: 0; 2026-03-02: 0; 2026-03-09: 0; 2026-03-16: 0; 2026-03-23: 0; 2026-03-30: 0
NMIP25018 | Xcel SPS HB Texas | 100% | 0 | 0 | 0 | 0% | 2025-06-30: 0; 2025-07-07: 0; 2025-07-14: 0; 2025-07-21: 0; 2025-07-28: 0; 2025-08-04: 0; 2025-08-11: 0; 2025-08-18: 0; 2025-08-31: 0; 2025-09-01: 0; 2025-09-08: 0; 2025-09-15: 0; 2025-09-22: 0; 2025-09-29: 0; 2025-10-06: 0; 2025-10-13: 0; 2025-10-20: 0; 2025-10-27: 0; 2025-11-03: 0; 2025-11-10: 0; 2025-11-17: 0; 2025-11-24: 0; 2025-12-01: 0; 2025-12-08: 0; 2025-12-15: 0; 2025-12-22: 0; 2025-12-29: 0; 2026-01-05: 0; 2026-01-12: 0; 2026-01-19: 0; 2026-01-26: 0; 2026-02-02: 0; 2026-02-09: 0; 2026-02-16: 0; 2026-02-23: 0; 2026-03-02: 0; 2026-03-09: 0; 2026-03-16: 0; 2026-03-23: 0; 2026-03-30: 0
NMAP25108 | Powerlink CopperString | 100% | 195.5 | 105 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.375 | 6.375 | 25.925 | 52.275 | 39.1 | 33.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.75 | 12.75 | 0 | 0 | 0 | 6.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP25049 | Minnkota PC 2025 | 100% | 0 | 237 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP25066 | FPL 2025 | 100% | 0 | 562 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP25054 | SoCo APC 2025 | 100% | 0 | N/A | 0 | 0% | 2025-06-30: 0; 2025-07-07: 0; 2025-07-14: 0; 2025-07-21: 0; 2025-07-28: 0; 2025-08-04: 0; 2025-08-11: 0; 2025-08-18: 0; 2025-08-31: 0; 2025-09-01: 0; 2025-09-08: 0; 2025-09-15: 0; 2025-09-22: 0; 2025-09-29: 0; 2025-10-06: 0; 2025-10-13: 0; 2025-10-20: 0; 2025-10-27: 0; 2025-11-03: 0; 2025-11-10: 0; 2025-11-17: 0; 2025-11-24: 0; 2025-12-01: 0; 2025-12-08: 0; 2025-12-15: 0; 2025-12-22: 0; 2025-12-29: 0; 2026-01-05: 0; 2026-01-12: 0; 2026-01-19: 0; 2026-01-26: 0; 2026-02-02: 0; 2026-02-09: 0; 2026-02-16: 0; 2026-02-23: 0; 2026-03-02: 0; 2026-03-09: 0; 2026-03-16: 0; 2026-03-23: 0; 2026-03-30: 0
NMIP25057 | SoCo GPC 2025 | 100% | 0 | N/A | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP25010 | Eversource 2025 | 100% | 0 | 60 | 0 | 0% | 2025-06-30: 0; 2025-07-07: 0; 2025-07-14: 0; 2025-07-21: 0; 2025-07-28: 0; 2025-08-04: 0; 2025-08-11: 0; 2025-08-18: 0; 2025-08-31: 0; 2025-09-01: 0; 2025-09-08: 0; 2025-09-15: 0; 2025-09-22: 0; 2025-09-29: 0; 2025-10-06: 0; 2025-10-13: 0; 2025-10-20: 0; 2025-10-27: 0; 2025-11-03: 0; 2025-11-10: 0; 2025-11-17: 0; 2025-11-24: 0; 2025-12-01: 0; 2025-12-08: 0; 2025-12-15: 0; 2025-12-22: 0; 2025-12-29: 0; 2026-01-05: 0; 2026-01-12: 0; 2026-01-19: 0; 2026-01-26: 0; 2026-02-02: 0; 2026-02-09: 0; 2026-02-16: 0; 2026-02-23: 0; 2026-03-02: 0; 2026-03-09: 0; 2026-03-16: 0; 2026-03-23: 0; 2026-03-30: 0
NMIP25067 | Xcel 5301 | 100% | 0 | N/A | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP25104 | Xcel NSP Fall 2025 | 100% | 0 | - | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP25091 | Xcel PSCo Fall | 100% | 0 | - | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMAP25126 | Powerlink MacIntyre | 100% | 108.375 | 60 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 6.8 | 13.175 | 13.6 | 54.4 | 6.8 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMAP26001 | Transgrid 2026 | 100% | 5109.775 | 6762 | 0 | [28 empty] | 0 | 0 | 0 | 47.6 | 68 | 102 | 142.8 | 224.4 | 393.975 | 506.6 | 494.7 | 526.575 | 431.8 | 411.4 | 534.225 | 499.375 | 425.85 | 135.15 | 124.525 | 40.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP25052 | LGE Spring 2025 | 100% | 0 | 343 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMLP24104 | SSE BDUP | 100% | 0 | 150 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP25086 | NGUS ACR | 100% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP25088 | NGUS Fall TLE | 100% | 0 | 146 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP25109 | Ameren Drone | 100% | 0 | 0 | 0 | 0% | 2025-06-30: 0; 2025-07-07: 0; 2025-07-14: 0; 2025-07-21: 0; 2025-07-28: 0; 2025-08-04: 0; 2025-08-11: 0; 2025-08-18: 0; 2025-08-31: 0; 2025-09-01: 0; 2025-09-08: 0; 2025-09-15: 0; 2025-09-22: 0; 2025-09-29: 0; 2025-10-06: 0; 2025-10-13: 0; 2025-10-20: 0; 2025-10-27: 0; 2025-11-03: 0; 2025-11-10: 0; 2025-11-17: 0; 2025-11-24: 0; 2025-12-01: 0; 2025-12-08: 0; 2025-12-15: 0; 2025-12-22: 0; 2025-12-29: 0; 2026-01-05: 0; 2026-01-12: 0; 2026-01-19: 0; 2026-01-26: 0; 2026-02-02: 0; 2026-02-09: 0; 2026-02-16: 0; 2026-02-23: 0; 2026-03-02: 0; 2026-03-09: 0; 2026-03-16: 0; 2026-03-23: 0; 2026-03-30: 0
NMCP25083 | HONI 115 kV Reporting | 100% | 0 | 80 | 0 | 0% | 2025-09-08: 0; 2025-09-15: 0; 2025-09-22: 0; 2025-09-29: 0; 2025-10-06: 0; 2025-10-13: 0; 2025-10-20: 0; 2025-10-27: 0; 2025-11-03: 0; 2025-11-10: 0; 2025-11-17: 0; 2025-11-24: 0; 2025-12-01: 0; 2025-12-08: 0; 2025-12-15: 0; 2025-12-22: 0; 2025-12-29: 0; 2026-01-05: 0; 2026-01-12: 0; 2026-01-19: 0; 2026-01-26: 0; 2026-02-02: 0; 2026-02-09: 0; 2026-02-16: 0; 2026-02-23: 0; 2026-03-02: 0; 2026-03-09: 0; 2026-03-16: 0; 2026-03-23: 0; 2026-03-30: 0
NMIP25103 | Xcel MNEC | 100% | 0 | - | 0 |  | 2025-10-13: 0; 2025-10-20: 0; 2025-10-27: 0; 2025-11-03: 0; 2025-11-10: 0; 2025-11-17: 0; 2025-11-24: 0; 2025-12-01: 0; 2025-12-08: 0; 2025-12-15: 0; 2025-12-22: 0; 2025-12-29: 0; 2026-01-05: 0; 2026-01-12: 0; 2026-01-19: 0; 2026-01-26: 0; 2026-02-02: 0; 2026-02-09: 0; 2026-02-16: 0; 2026-02-23: 0; 2026-03-02: 0; 2026-03-09: 0; 2026-03-16: 0; 2026-03-23: 0; 2026-03-30: 0
NMIP25098 | LGE Fall (Eng) | 100% | 0 | 167 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMAP26036 | Humelink Canopies | 30.7% | 224.4 | 88 | 54.4 | 75.76% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 34 | 34 | 0 | 34 | 47.6 | 20.4 | 0 | 54.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMLP25003 | NGUK 2025 | 100% | 0 | N/A | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP25093 | SoCo GPC Engr | 100% | 0 | 49 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP25038 | Avangrid CMP Engr | 100% | 505.75 | 345 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6 | 0 | 0 | 0 | 0 | 0 | 12.75 | 93.075 | 59.075 | 20.4 | 0 | 0 | 12.75 | 0 | 0 | 0 | 12.75 | 38.25 | 31.875 | 31.875 | 51 | 95.625 | 19.125 | 0 | 0 | 0 | 0 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP25119 | ComEd Wood to Steel | 100% | 0 | 284 | 0 |  | 2026-03-23: 0; 2026-03-30: 0; 2026-04-06: 0; 2026-04-13: 0; 2026-04-20: 0; 2026-04-27: 0; 2026-05-04: 0; 2026-05-11: 0; 2026-05-18: 0; 2026-05-25: 0; 2026-06-01: 0; 2026-06-08: 0; 2026-06-15: 0; 2026-06-22: 0; 2026-06-29: 0; 2026-07-06: 0; 2026-07-13: 0; 2026-07-20: 0; 2026-07-27: 0; 2026-08-03: 0; 2026-08-10: 0; 2026-08-17: 0; 2026-08-24: 0; 2026-08-31: 0; 2026-09-07: 0; 2026-09-14: 0; 2026-09-21: 0; 2026-09-28: 0; 2026-10-05: 0; 2026-10-12: 0; 2026-10-19: 0; 2026-10-26: 0; 2026-11-02: 0; 2026-11-09: 0; 2026-11-16: 0; 2026-11-23: 0; 2026-11-30: 0; 2026-12-07: 0; 2026-12-14: 0; 2026-12-21: 0; 2026-12-28: 0; 2027-01-04: 0; 2027-01-11: 0
NMIP25122 | NGUS S1 U2 Mapping | 100% | 0 | - | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP25151 | NV Energy 2025 | 100% | 0 | 426 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMCP25092 | HONI Max Op | 100% | 1129.225 | 2025 | 0 | [28 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 19.125 | 6.375 | 0 | 79.9 | 174.675 | 53.55 | 0 | 0 | 25.925 | 73.525 | 132.6 | 113.9 | 154.275 | 181.475 | 107.525 | 6.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMCP25127 | HONI 500kV | 72% | 93.925 | 86 | 6.375 | 93.21% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 13.6 | 13.6 | 20.4 | 20.4 | 0 | 19.55 | 6.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26009 | Ameren UAV Processing | 100% | 87.55 | 44 | 0 | [28 empty] | 0 | 0 | 0 | 0 | 6.8 | 13.6 | 6.375 | 6.8 | 6.8 | 27.2 | 19.975 | 0 | 0 | 6.8 | 27.2 | 13.6 | 0 | 0 | 0 | 34 | 0 | 6.8 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMCP26023 | HONI 2026 | 2% | 6305.3 | 6298 | 6137 | [28 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 47.6 | 107.525 | 6.375 | 0 | 0 | 0 | 0 | 0 | 68 | 86.7 | 226.95 | 233.75 | 255 | 356.15 | 295.8 | 335.75 | 403.75 | 331.075 | 290.275 | 303.875 | 303.875 | 284.75 | 371.875 | 403.75 | 396.95 | 383.35 | 403.75 | 133.875 | 133.875 | 133.875 | 0 | 0 | 0 | 0
NMIP26009 | Ameren UAV Processing | 100% | 87.55 | 0 | 0 | [28 empty] | 0 | 0 | 0 | 0 | 6.8 | 13.6 | 6.375 | 6.8 | 6.8 | 27.2 | 19.975 | 0 | 0 | 6.8 | 27.2 | 13.6 | 0 | 0 | 0 | 34 | 0 | 6.8 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26011 | Xcel HB 2026 | 100% | 0 | 930 | 0 | [28 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26014 | LS Power Collinsville | 100% | 0 | 16 | 0 |  | 2026-03-23: 0; 2026-03-30: 0; 2026-04-06: 0; 2026-04-13: 0; 2026-04-20: 0; 2026-04-27: 0; 2026-05-04: 0; 2026-05-11: 0; 2026-05-18: 0; 2026-05-25: 0; 2026-06-01: 0; 2026-06-08: 0; 2026-06-15: 0; 2026-06-22: 0; 2026-06-29: 0; 2026-07-06: 0; 2026-07-13: 0; 2026-07-20: 0; 2026-07-27: 0; 2026-08-03: 0; 2026-08-10: 0; 2026-08-17: 0; 2026-08-24: 0; 2026-08-31: 0; 2026-09-07: 0; 2026-09-14: 0; 2026-09-21: 0; 2026-09-28: 0; 2026-10-05: 0; 2026-10-12: 0; 2026-10-19: 0; 2026-10-26: 0; 2026-11-02: 0; 2026-11-09: 0; 2026-11-16: 0; 2026-11-23: 0; 2026-11-30: 0; 2026-12-07: 0; 2026-12-14: 0; 2026-12-21: 0; 2026-12-28: 0; 2027-01-04: 0; 2027-01-11: 0
NMLP24118 | SSE SHET | 100% | 0 | 1825 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26019 | Xcel PSCo & SPS | 100% | 0 | 410 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMCP26060 | HONI Darlington Nuclear | 0% | 0 | 16 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26003 | FPL Winter 2026 | 100% | 2125.2125 | 1689 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6 | 95.2 | 81.6 | 27.2 | 127.5 | 20.4 | 114.325 | 19.55 | 0 | 110.925 | 150.45 | 164.05 | 190.825 | 230.35 | 184.025 | 170 | 211.8625 | 136 | 77.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP25104-1 | Xcel W3419 | 100% | 0 | 0 | 0 | [28 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26002 | CHGE Spring 2026 | 88% | 745.025 | 333 | 154.7 | 79.24% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 6.8 | 20.4 | 68 | 20.4 | 0 | 52.275 | 79.475 | 174.675 | 168.3 | 154.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMCP26037 | HONI DKPL2 | 100% | 33.15 | 8 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 13.6 | 6.8 | 12.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26008 | Avangrid CMP Veg 2026 | 73% | 620.075 | 684 | 188.275 | 69.64% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 33.575 | 66.3 | 54.4 | 27.2 | 68 | 27.2 | 68 | 87.125 | 86.275 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26025 | Sunflower Electric | 70% | 909.925 | 1170 | 733.125 | 19.43% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.6 | 27.2 | 20.4 | 20.4 | 95.2 | 167.875 | 167.875 | 201.875 | 65.875 | 31.875 | 31.875 | 65.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26027 | NYPA Group A 2026 | 27% | 2659.65 | 2584 | 2125 | 20.1% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 19.125 | 6.375 | 45.9 | 141.525 | 39.95 | 107.1 | 67.575 | 107.1 | 88.4 | 288.15 | 465.375 | 413.1 | 359.125 | 306.85 | 68 | 68 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26029 | NGUS 2026 | 0% | 3153.5 | 3198 | 3153.5 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 34 | 102 | 68 | 0 | 47.6 | 0 | 0 | 0 | 169.15 | 269.875 | 269.875 | 269.875 | 269.875 | 269.875 | 269.875 | 269.875 | 269.875 | 269.875 | 269.875 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26030 | OPPD 2026 | 88% | 828.75 | 572 | 208.25 | 74.87% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 3.4 | 0 | 6.8 | 53.125 | 68 | 6.8 | 0 | 47.6 | 95.2 | 27.2 | 183.175 | 129.2 | 112.625 | 95.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26032 | Westwood Minnesota | 100% | 13.175 | 24 | 6.8 | 48.39% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.375 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26031 | Eversource 2026 | 0% | 1022.55 | 1020 | 1022.55 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 68 | 0 | 34 | 0 | 0 | 0 | 6.8 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 99.875 | 133.875 | 0 | 0 | 0 | 0 | 0
NMIP26035 | ComEd CSX | 37% | 6.8 | 52 | 0 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26041 | CMP Eng 2026 | 0% | 0 | 100 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26043 | Xcel NSP Spring 2026 | 2% | 1298.375 | 1610 | 1135.175 | 12.57% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 27.2 | 68 | 34 | 46.325 | 226.95 | 322.15 | 301.75 | 140.25 | 65.875 | 31.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26055 | SoCo GPC 2026 | 0% | 2565.725 | 2570 | 2555.525 | 0.3975% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 3.4 | 39.95 | 61.2 | 95.2 | 136 | 236.3 | 263.075 | 201.875 | 320.45 | 234.175 | 267.75 | 120.7 | 107.1 | 107.95 | 133.45 | 39.95 | 27.2 | 40.8 | 40.8 | 40.8 | 40.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26056 | SoCo APC 2026 | 0% | 2397.425 | 2320 | 2397.425 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.4 | 0 | 34 | 136 | 122.4 | 156.4 | 54.4 | 181.475 | 210.8 | 176.8 | 156.4 | 229.925 | 168.725 | 193.8 | 174.675 | 113.475 | 113.475 | 127.075 | 27.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMLP25094 | SHET RIIO-T3 | 18% | 1420.775 | 5563 | 465.8 | 67.22% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 27.2 | 68 | 270.3 | 297.075 | 156.4 | 27.2 | 61.2 | 47.6 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204 | 167.875 | 80.325 | 0 | 0 | 0 | 0
NMLP26012 | WSP EDN2 | 0% | 20.4 | 95 | 20.4 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26020 | FPL Summer 2026 | 0% | 1126.25 | 0 | 1126.25 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 133.875 | 91.375 | 38.25 | 63.75 | 63.75 | 63.75 | 63.75 | 63.75 | 63.75 | 63.75 | 63.75 | 63.75 | 63.75 | 63.75 | 63.75 | 63.75 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26038 | Lansing BWL 2026 | 0% | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NMIP26042 | PG&E M4 |  | 2908.7 | 0 | 2908.7 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.875 | 65.875 | 65.875 | 99.875 | 87.125 | 87.125 | 99.875 | 111.775 | 105.4 | 131.75 | 131.75 | 131.75 | 131.75 | 131.75 | 131.75 | 131.75 | 124.95 | 97.75 | 131.75 | 131.75 | 131.75 | 131.75 | 131.75 | 131.75 | 105.4 | 79.05 | 0 | 0
NMIP26044 | LGE Spring 2026 | 0% | 131.75 | 0 | 131.75 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.875 | 65.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Administrative |  | 257.55 |  | 27.2 | 89.44% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.4 | 0 | 6.8 | [11 empty] | 6.375 | 0 | 13.6 | 0 | 13.6 | 27.2 | 20.4 | 27.2 | 61.2 | 19.975 | 13.6 | 0 | 13.6 | 0 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FLOW |  | 1761.2 |  | 1210.4 |  | 2026-03-23: 27.2; 2026-03-30: 6.8; 2026-04-06: 6.8; 2026-04-13: 13.6; 2026-04-20: 34; 2026-04-27: 34; 2026-05-04: 47.6; 2026-05-11: 34; 2026-05-18: 66.3; 2026-05-25: 46.75; 2026-06-01: 65.875; 2026-06-08: 167.875; 2026-06-15: 136; 2026-06-22: 136; 2026-06-29: 129.2; 2026-07-06: 136; 2026-07-13: 136; 2026-07-20: 136; 2026-07-27: 136; 2026-08-03: 34; 2026-08-10: 34; 2026-08-17: 34; 2026-08-24: 34; 2026-08-31: 27.2; 2026-09-07: 34; 2026-09-14: 34; 2026-09-21: 34; 2026-09-28: 0; 2026-10-05: 0; 2026-10-12: 0; 2026-10-19: 0; 2026-10-26: 0; 2026-11-02: 0; 2026-11-09: 0; 2026-11-16: 0; 2026-11-23: 0; 2026-11-30: 0; 2026-12-07: 0; 2026-12-14: 0; 2026-12-21: 0; 2026-12-28: 0; 2027-01-04: 0; 2027-01-11: 0
| QA Team |  | 1407.6 |  | 136 | 90.34% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 129.2 | 108.8 | 95.2 | 88.4 | 108.8 | 95.2 | 81.6 | 95.2 | 102 | 129.2 | 122.4 | 115.6 | 88.4 | 47.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Training |  | 2560.625 |  | 27.2 | 98.94% | 156.4 | 149.6 | 163.2 | 149.6 | 136 | 102 | 95.2 | 68 | 54.4 | 0 | 102 | 68 | 68 | 68 | 68 | 68 | 54.4 | 61.2 | 107.1 | 194.65 | 100.725 | 94.35 | 108.375 | 94.35 | 87.55 | 40.8 | 0 | [11 empty] | 33.575 | 19.975 | 0 | 6.8 | 6.375 | 0 | 0 | 0 | 0 | 0 | 6.8 | 0 | 27.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| UAT |  | 431.8 |  | 61.2 | 85.83% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.8 | 13.6 | 0 | [11 empty] | 0 | 0 | 0 | 13.6 | 20.4 | 61.2 | 0 | 12.75 | 33.15 | 54.4 | 100.3 | 54.4 | 61.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | CAPACITY | CAPACITY | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[5 empty] | ALLOCATED | ALLOCATED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 68 | 68 | 68 | 68 | 68 | 68 | 61.2 | 107.1 | 194.65 | 100.725 | 94.35 | 121.125 | 187.425 | 173.825 | 74.8 | 6.8 | 0 | 19.125 | 19.975 | 168.725 | 215.475 | 208.25 | 374 | 296.65 | 553.775 | 711.45 | 804.95 | 916.725 | 731 | 725.05 | 1068.45 | 1208.275 | 1249.5 | 1007.25 | 1200.4125 | 1229.525 | 866.575 | 1106.7 | 1062.5 | 1103.725 | 1166.2 | 1227.4 | 1152.6 | 1105.425 | 1093.95 | 880.6 | 960.925 | 1008.525 | 1067.175 | 1038.275 | 730.15 | 903.125 | 935.425 | 970.275 | 1025.525 | 991.525 | 991.525 | 986 | 966.45 | 903.125 | 930.325 | 916.725 | 937.125 | 903.125 | 567.375 | 345.95 | 105.4 | 79.05 | 0 | 0
[5 empty] | RS Shortage | RS Shortage
[5 empty] | GIS Shortage | GIS Shortage
[5 empty] | PLS Shortage | PLS Shortage
[5 empty] | BALLANCE | BALLANCE | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Note on F75: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @dominic.wilson@nmgroup.com are the processing hours for each project diminished with the QA effort? Assigned to dominic.wilson@nmgroup.com Reply: A follow up from me is that it doesn't work for Projects to have this bucket of 4,000 undefined by project. For cost forecasting we need to know future hours by projects. Can't the QA team be assigned to actual project codes rather than this undefined bucket?